## JobPOTrack
Data
Job No_ | Project Manager | Status | Document No_ | Vendor Name | Line No_ | Description | Total PO Amount | Total Paid on PO | Amount left on PO
J101394 | Bill Farrell | 2 | PO-103052 | Fosdick & Hilmer | 10000 | Professional Consulting Services for FWA 336A | 6937.5 | 6937.5 | 0
|  |  | PO-103052 Total |  |  |  | 6937.5 | 6937.5 | 0
|  |  | PO-103267 | Dryden & Larue Inc | 10000 | Design & Engineering Support | 20000 | 16391.95 | 3608.05
[5 empty] | 25000 | correction for receipting error | -1503.5 | -1503.5 | 0
[5 empty] | 27500 | correction for receipting error | 1503.5 | 1503.5 | 0
|  |  | PO-103267 Total |  |  |  | 20000 | 16391.95 | 3608.05
|  |  | PO-103349 | Riddle Consulting, Inc. | 38437 | Open PO for Riddle Consulting for 2010 Year | 2049.75 | 2049.75 | 0
|  |  | PO-103349 Total |  |  |  | 2049.75 | 2049.75 | 0
|  |  | PO-103730 | Fullford Electric, Inc. | 10000 | Labor to Construct FTW336A Aircraft Parts Storage | 63490 | 63490 | 0
[5 empty] | 20000 | CO # 1 - Material and Labor for Light Pole Bases | 6018.12 | 4748.22 | 1269.9
|  |  | PO-103730 Total |  |  |  | 69508.12 | 68238.22 | 1269.9
|  |  | PO-104016 | North Coast Electric | 10000 | Misc. Materials for 336A Aircraft Part Facility | 5000 | 4232.27 | 767.73
|  |  | PO-104016 Total |  |  |  | 5000 | 4232.27 | 767.73
|  |  | PO-103551 | Fairbanks Precast & Rebar | 40000 | SUM 1-B for New EDS Utility Service for FTW 336A | 1095 | 1095 | 0
|  |  | PO-103551 Total |  |  |  | 1095 | 1095 | 0
|  |  | PO-103507 | Potelcom Supply | 10000 | 300kVA 12470/480 Y: Y Padmount | 10546 | 10546 | 0
|  |  | PO-103507 Total |  |  |  | 10546 | 10546 | 0
|  |  | PO-103691 | Potelcom Supply | 10000 | 1/0 CONC 15kV AL, FULL NEUTRAL, 133% INSULATION | 550 | 550 | 0
[5 empty] | 20000 | 250kcmil XHHW, 600V | 787.5 | 787.5 | 0
[5 empty] | 30000 | #2/0 XHHW, 600V | 2710 | 2710 | 0
[5 empty] | 40000 | #2 SECONDARY QUADRUPLEX AL UNDERGROUND | 151.5 | 151.5 | 0
[5 empty] | 50000 | #4 XHHW, 600V | 250 | 250 | 0
[5 empty] | 60000 | 1PH OVERHEAD CONVENTIONAL TRANSFORMER (50 kVA) | 1849.33 | 1849.33 | 0
[5 empty] | 70000 | GROUNDING ASSEMBLY - GROUND ROD TYPE | 54.81 | 54.81 | 0
[5 empty] | 80000 | ELBOW CONDUIT 4" RIGID STEEL SHORT SWEEP 90° 36"R | 223.3 | 223.3 | 0
[5 empty] | 90000 | ELBOW CONDUIT 2.5" RIGID STEEL SHORT SWEEP 90°18"R | 90 | 90 | 0
[5 empty] | 100000 | ELBOW, CONDUIT 2" RIGID STEEL SHORT SWEEP 90°24"R | 73.1 | 73.1 | 0
[5 empty] | 110000 | 100A 240V SITE LIGHTING LOAD CENTER | 4041.63 | 4041.63 | 0
[5 empty] | 120000 | 400A SERVICE STD BREAKER CT-CAN METER SOCKET | 4027 | 4027 | 0
[5 empty] | 130000 | 3PH CABLE TERM. POLE DEADEND W/CUTOUTS & ARRESTERS | 1496.97 | 1496.97 | 0
[5 empty] | 140000 | 3PH PAD MOUNTED TRANS. LOOP FEED W/RADIAL 300 kVA | 465.63 | 465.63 | 0
[5 empty] | 150000 | SECONDARY CABLE TERMINAL POLE | 281.45 | 281.45 | 0
[5 empty] | 160000 | GROUND ROD ASSEMBLY | 14.69 | 14.69 | 0
[5 empty] | 170000 | CONDUIT, 4" HDPE - SCHEDULE 40 | 165.6 | 165.6 | 0
[5 empty] | 180000 | CONDUIT, 2" HDPE - SCHEDULE 40 | 80 | 80 | 0
[5 empty] | 190000 | CONDUIT, 1" HDPE - SCHEDULE 40 | 212.4 | 212.4 | 0
[5 empty] | 200000 | CONDUIT, 4" GALVANIZED RIGID STEEL | 413.1 | 413.1 | 0
[5 empty] | 210000 | CONDUIT, 2.5" GALVANIZED RIGID STEEL | 924 | 924 | 0
[5 empty] | 220000 | CONDUIT, 2" GALVANIZED RIGID STEEL | 159.6 | 159.6 | 0
[5 empty] | 230000 | LOAD BREAK ELBOW (200A) | 140.85 | 140.85 | 0
[5 empty] | 240000 | #12 CU 600V, XHHW Black | 125 | 125 | 0
[5 empty] | 250000 | #12 CU 600V, XHHW White | 125 | 125 | 0
[5 empty] | 260000 | #12 CU 600V, XHHW Green | 125 | 125 | 0
[5 empty] | 270000 | 30' Steel Pole | 5780 | 5780 | 0
|  |  | PO-103691 Total |  |  |  | 25317.46 | 25317.46 | 0
J101394 Total | [6 empty] | 140453.83 | 134808.15 | 5645.68
J101395 | Wily Splain | 2 | PO-103052 | Fosdick & Hilmer | 20000 | Professional Consulting Services for FWA 336A | 10020.84 | 10020.84 | 0
|  |  | PO-103052 Total |  |  |  | 10020.84 | 10020.84 | 0
|  |  | PO-103576 | Perma-Pipe | 15000 | Direct Bury Pipe for 336A | 20143 | 20143 | 0
[5 empty] | 16250 | Direct Bury Pipe for 336A | -16802 | -16802 | 0
[5 empty] | 16875 | Direct Bury Pipe for 336A | 16802 | 16802 | 0
[5 empty] | 17500 | Expedited Shipping | 4282 | 4282 | 0
[5 empty] | 18125 | Expedited Shipping | -4282 | -4282 | 0
[5 empty] | 18437 | Expedited Shipping | 4282 | 4282 | 0
|  |  | PO-103576 Total |  |  |  | 24425 | 24425 | 0
|  |  | PO-103639 | Maynard Reece | 10000 | Prowil 3" Steam Meter #73F80-SK4AA1NAB4AA | 4935 | 4935 | 0
[5 empty] | 20000 | Plate Conditioner 35 Hole 3" #DK7ST-80K0 | 590 | 590 | 0
|  |  | PO-103639 Total |  |  |  | 5525 | 5525 | 0
|  |  | PO-103653 | Badger Meter | 40000 | Model 350T Transmitter for Steam Meters, 20' Lead | 210 | 210 | 0
[5 empty] | 45000 | Shipping Charges | 57.28 | 57.28 | 0
|  |  | PO-103653 Total |  |  |  | 267.28 | 267.28 | 0
|  |  | PO-103909 | Tunista Arctic Rim/TBI Const | 10000 | Utilidors and Access Vaults | 298604.8 | 250387.25 | 48217.55
[5 empty] | 20000 | Utilidor and Direct Buried HDS Mains | 186628 | 53142 | 133486
|  |  | PO-103909 Total |  |  |  | 485232.8 | 303529.25 | 181703.55
|  |  | PO-104026 | Paragon General Construction | 10000 | Quality Assurance for 336A Aircraft Storage | 6666.67 | 2400.42 | 4266.25
|  |  | PO-104026 Total |  |  |  | 6666.67 | 2400.42 | 4266.25
|  |  | PO-104343 | Fosdick & Hilmer | 10000 | Construction Consulting for FTW 336A | 8840 | 3536 | 5304
[5 empty] | 48750 | Construction Consulting for FTW 336A | 4420 | 4420 | 0
|  |  | PO-104343 Total |  |  |  | 13260 | 7956 | 5304
|  |  | PO-103647 | Ferguson Enterprise Inc. | 550000 | 3 IMP BLK PE A106B 40 SMLS SRL | 1825.6 | 1825.6 | 0
[5 empty] | 560000 | 2 IMP BLK PE A106B 40 SMLS SRL | 69.73 | 69.73 | 0
[5 empty] | 570000 | 1-1/2 IMP BLK PE A106B 40 SMLS SRL | 61.62 | 61.62 | 0
[5 empty] | 580000 | 3/4 IMP BLK PE A106B 40 SMLS SRL | 28.89 | 28.89 | 0
[5 empty] | 585000 | 6 BLK PE A106B 40 SMLS SRL PIPE | 56.97 | 56.97 | 0
[5 empty] | 590000 | 3 CS STD WELD LR 90 ELL | 249.36 | 249.36 | 0
[5 empty] | 600000 | 2 FS 3000# SOC 90 ELL | 41.78 | 41.78 | 0
[5 empty] | 610000 | 3 CS STD WELD 45 ELL | 81.09 | 81.09 | 0
[5 empty] | 620000 | 3 CS STD WELD TEE | 87.5 | 87.5 | 0
[5 empty] | 630000 | 2 FS 3000# SOC TEE | 28.71 | 28.71 | 0
[5 empty] | 640000 | 2X2X3/4 FS 3000# SOC TEE | 56.97 | 56.97 | 0
[5 empty] | 650000 | 3X2 CS STD WELD ECC RED | 20.77 | 20.77 | 0
[5 empty] | 660000 | 2X3/4 FS 3000# SOC RED | 36.89 | 36.89 | 0
[5 empty] | 670000 | 2 FS 3000# SOC COUP | 16.32 | 16.32 | 0
[5 empty] | 680000 | 3/4 FS 3000# SOC COUP | 6.26 | 6.26 | 0
[5 empty] | 690000 | 2 FS 3000# SOC STL STL UNION | 35.87 | 35.87 | 0
[5 empty] | 700000 | 3/4 FS 3000# SOC STL STL UNION | 22 | 22 | 0
[5 empty] | 710000 | 3 CS STD WELD CAP | 16.1 | 16.1 | 0
[5 empty] | 720000 | 1-1/2 FS 3000# SOC COUP | 17.01 | 17.01 | 0
[5 empty] | 730000 | 3/4 TD-52 STM TRAP | 1175.76 | 1175.76 | 0
[5 empty] | 740000 | 3/4 CS 600# SW PERF Y STRN | 247.39 | 247.39 | 0
[5 empty] | 750000 | 3 VELAN 150# BW CS FP GATE VLV | 1077.53 | 1077.53 | 0
[5 empty] | 760000 | 2 APOLLO 600# SW FP CS BALL VLV | 998.68 | 998.68 | 0
[5 empty] | 770000 | 2 VELAN 800# SW CS SWING CHK VLV | 287.89 | 287.89 | 0
[5 empty] | 780000 | 1-1/2 APOLLO 600# SW FP CS BALL VLV | 2745.38 | 2745.38 | 0
[5 empty] | 790000 | 3/4 APOLLO 600# SW FP CS BALL VLV | 1586.15 | 1586.15 | 0
[5 empty] | 800000 | 1-1/2 SS SCH10 316L A312 WELD PIPE | 1714.32 | 1714.32 | 0
[5 empty] | 810000 | 1 SS SCH10 316L A312 WELD PIPE | 498.9 | 498.9 | 0
[5 empty] | 820000 | 3/4 SS SCH10 316L A312 WELD PIPE | 131.44 | 131.44 | 0
[5 empty] | 830000 | 1-1/2 SS 316L 3000# SOC 90 ELL | 565.25 | 565.25 | 0
[5 empty] | 840000 | 1 SS 316L 3000# SOC 90 ELL | 110.57 | 110.57 | 0
[5 empty] | 850000 | 3/4 SS 316L 3000# SOC 90 ELL | 148.34 | 148.34 | 0
[5 empty] | 860000 | 1-1/2 SS 316L 3000# SOC 45 ELL | 221.81 | 221.81 | 0
[5 empty] | 870000 | 1 SS 316L 3000# SOC 45 ELL | 55.95 | 55.95 | 0
[5 empty] | 880000 | 3/4 SS 316L 3000# SOC 45 ELL | 92.65 | 92.65 | 0
[5 empty] | 890000 | 1-1/2 SS 316L 3000# SOC COUP | 146.67 | 146.67 | 0
[5 empty] | 900000 | 1 SS 316L 3000# SOC COUP | 28.04 | 28.04 | 0
[5 empty] | 910000 | 3/4 SS 316L 3000# SOC UNION | 63.35 | 63.35 | 0
[5 empty] | 920000 | 1 SS 316L 3000# SOC UNION | 25.48 | 25.48 | 0
[5 empty] | 930000 | 1-1/2 APOLLO 600# SW FP CS BALL VLV | 795.56 | 795.56 | 0
[5 empty] | 940000 | 1-1/2 VELAN 800# SW SS SWING CHK VL | 1492.58 | 1492.58 | 0
[5 empty] | 950000 | 3/4 VELAN 800# SW SS SWING CHK VLV | 3132.97 | 3132.97 | 0
[5 empty] | 960000 | 3/4 APOLLO 600# SW FP CS BALL VLV | 906.37 | 906.37 | 0
[5 empty] | 970000 | 1 APOLLO 600# SW FP CS BALL VLV | 289.34 | 289.34 | 0
[5 empty] | 980000 | 3/4X12 SS FLEX W/ SS SW ENDS | 363.95 | 363.95 | 0
[5 empty] | 990000 | 1X12 SS FLEX W/ SS SW ENDS | 111.92 | 111.92 | 0
[5 empty] | 885000 | 3/4 SS 316L 3000# SOC TEE | 47.75 | 47.75 | 0
|  |  | PO-103647 Total |  |  |  | 21821.43 | 21821.43 | 0
J101395 Total | [6 empty] | 567219.02 | 375945.22 | 191273.8
J101396 | Wily Splain | 2 | PO-103052 | Fosdick & Hilmer | 30000 | Professional Consulting Services for FWA 336A | 10020.83 | 10020.83 | 0
|  |  | PO-103052 Total |  |  |  | 10020.83 | 10020.83 | 0
|  |  | PO-103490 | Panel-Fab, Inc. | 10000 | Control Panel #CP-G693 | 3748 | 3748 | 0
[5 empty] | 20000 | PLC & HMI Configuration and Programming provided | 4200 | 4200 | 0
[5 empty] | 40000 | Shipping | 300 | 300 | 0
|  |  | PO-103490 Total |  |  |  | 8248 | 8248 | 0
|  |  | PO-103653 | Badger Meter | 10000 | 2" Recordall M170 ELL, Bare,Low Lead Alloy Housing | 464 | 464 | 0
[5 empty] | 20000 | ADE and Orion Remote Module, 5/8"-2" Badger Disc | 115 | 115 | 0
[5 empty] | 47500 | Shipping Charges | 91.04 | 91.04 | 0
|  |  | PO-103653 Total |  |  |  | 670.04 | 670.04 | 0
|  |  | PO-103690 | Panel-Fab, Inc. | 10000 | Control Panel CP336AM | 789 | 789 | 0
[5 empty] | 20000 | Estimated Shipping | 130 | 130 | 0
|  |  | PO-103690 Total |  |  |  | 919 | 919 | 0
|  |  | PO-103776 | Vertex | 10000 | 6" DIP w/3" polyurethane foam | 855.4 | 855.4 | 0
[5 empty] | 15000 | 8" DIP w/2" polyurethane foam | 1529.45 | 1529.45 | 0
|  |  | PO-103776 Total |  |  |  | 2384.85 | 2384.85 | 0
|  |  | PO-103909 | Tunista Arctic Rim/TBI Const | 30000 | Utilidor and Direct Buried WDS Mains | 186628 | 53142 | 133486
|  |  | PO-103909 Total |  |  |  | 186628 | 53142 | 133486
|  |  | PO-104026 | Paragon General Construction | 20000 | Quality Assurance for 336A Aircraft Storage | 6666.67 | 1703.1 | 4963.57
|  |  | PO-104026 Total |  |  |  | 6666.67 | 1703.1 | 4963.57
|  |  | PO-104343 | Fosdick & Hilmer | 20000 | Construction Consulting for FTW 336A | 8840 | 3536 | 5304
[5 empty] | 49375 | Construction Consulting for FTW 336A | 4420 | 4420 | 0
|  |  | PO-104343 Total |  |  |  | 13260 | 7956 | 5304
|  |  | PO-103647 | Ferguson Enterprise Inc. | 20000 | 8 CL53 GRVXGRV DI PIPE | 1134.97 | 1134.97 | 0
[5 empty] | 30000 | 6 CL53 GRVXGRV DI PIPE | 414.2 | 414.2 | 0
[5 empty] | 40000 | 2 X 20 L HARD COP TUBE (includes groove fee) | 2703.05 | 2703.05 | 0
[5 empty] | 50000 | *CVR* A 8 90 LR ELL 100-C DI C/L T3 | 896.4 | 896.4 | 0
[5 empty] | 60000 | 2 COP GRV 90 ELL 610 | 371.4 | 371.4 | 0
[5 empty] | 70000 | 8 45 ELL 11-C CDI CL T37-77 | 291.64 | 291.64 | 0
[5 empty] | 80000 | 8 TEE 20-C CDI CL T37-77 | 198.8 | 198.8 | 0
[5 empty] | 90000 | *CVR* A 8X8X4 RD TEE 25-C DI C/L T3 | 451.33 | 451.33 | 0
[5 empty] | 100000 | 4 PTD TRANS COUP FS M GSKT 307 | 129.75 | 129.75 | 0
[5 empty] | 110000 | 4X2 PTD GRV CONC RED 50 | 51.33 | 51.33 | 0
[5 empty] | 120000 | 2X1 COP GRV X COP TEE 626 | 61.68 | 61.68 | 0
[5 empty] | 130000 | 2X3/4 COP GRV X COP TEE 626 | 61.65 | 61.65 | 0
[5 empty] | 140000 | *CVR* A 8X6 CONC 50-C DI C/L T3 050 | 206.34 | 206.34 | 0
[5 empty] | 150000 | 8 PTD GRV COUP F/ DIP 31 | 1886.96 | 1886.96 | 0
[5 empty] | 160000 | 6 PTD GRV COUP F/ DIP 31 | 232.58 | 232.58 | 0
[5 empty] | 170000 | 2 RIGID COUP F/ COP TUBE 607 | 699.89 | 699.89 | 0
[5 empty] | 180000 | 2 COP FLG ADPT GSKT 641 | 1283.72 | 1283.72 | 0
[5 empty] | 190000 | 2 BRZ 150# THRD 20 MESH Y STRN | 83.56 | 83.56 | 0
[5 empty] | 200000 | 8 FLG RW OL GATE VLV W/ H/WHL ZN | 1630.77 | 1630.77 | 0
[5 empty] | 210000 | 6 FLG RW OL GATE VLV W/ H/WHL ZN | 519 | 519 | 0
[5 empty] | 220000 | *CVR* 317 8 CKV 317 T37H-77 T SEAT | 1638.18 | 1638.18 | 0
[5 empty] | 230000 | 2 BRS 600# WOG SWT 2PC FP BV | 366.27 | 366.27 | 0
[5 empty] | 240000 | 3/4 BRS 600# WOG SWT 2PC FP BV | 10.2 | 10.2 | 0
[5 empty] | 250000 | 8 DI PIPE CL50 TYTON JT | 2609.12 | 2609.12 | 0
[5 empty] | 260000 | 6 DI PIPE CL50 TYTON JT | 1152.24 | 1152.24 | 0
[5 empty] | 270000 | 1X100 K SOFT COP TUBE | 588.79 | 588.79 | 0
[5 empty] | 280000 | 8 MJ C153 90 BEND L/A | 107.49 | 107.49 | 0
[5 empty] | 290000 | 1 FLR 90 BEND | 67.14 | 67.14 | 0
[5 empty] | 300000 | 8X6 MJ C153 SWVL TEE L/A | 152.9 | 152.9 | 0
[5 empty] | 310000 | 8 ROMAGRIP ACCY PK F/ DI | 442.96 | 442.96 | 0
[5 empty] | 320000 | 6 ROMAGRIP ACCY PK F/ DI | 573.28 | 573.28 | 0
[5 empty] | 330000 | 1 FLR X MIP COUP | 42.59 | 42.59 | 0
[5 empty] | 340000 | 6 MJ RW DI OL GATE VLV L/A | 496.62 | 496.62 | 0
[5 empty] | 350000 | 5x5 SV SH soil pipe | 91.6 | 91.6 | 0
[5 empty] | 360000 | 18 TOP SECTION F/ VB | 30.22 | 30.22 | 0
[5 empty] | 370000 | 1 BOT SECT F/ VB | 33.9 | 33.9 | 0
[5 empty] | 380000 | PAVING SLV LID ONLY - WTR | 10.48 | 10.48 | 0
[5 empty] | 390000 | VLV BX DUST CUP | 9.66 | 9.66 | 0
[5 empty] | 400000 | 5-1/4 BURY HYD 5'0 16 TRAFFIC 6 FLG | 1922.18 | 1922.18 | 0
[5 empty] | 410000 | 4X5X53 STL HYD MRKR W/ POLY FLAG | 32.42 | 32.42 | 0
[5 empty] | 420000 | 6 FLG TYTE GSKT | 11.43 | 11.43 | 0
[5 empty] | 430000 | 6 150# BOLT KIT 8 3/4X3-1/4 IMP | 9.01 | 9.01 | 0
[5 empty] | 440000 | 6 MJ C153 ACC PK | 15.17 | 15.17 | 0
|  |  | PO-103647 Total |  |  |  | 23722.87 | 23722.87 | 0
|  |  | PO-103701 | CB Engineering Pacific Inc. | 10000 | Greystone Ambient air Temp. Trans.#TE500AS12GS003 | 136.74 | 136.74 | 0
[5 empty] | 20000 | Greystone Temp/Humd Trans. #RH310A03C1A6 | 253.07 | 253.07 | 0
[5 empty] | 30000 | Direct Mount Gauge Pressure Transmitter | 642.81 | 642.81 | 0
[5 empty] | 50000 | Two Valve Manifold #PV-614SCG | 237.92 | 237.92 | 0
[5 empty] | 60000 | Differential Pressure Transmitter | 989.45 | 989.45 | 0
[5 empty] | 80000 | 12" Verabar Primary Flow Element | 2012.9 | 2012.9 | 0
[5 empty] | 100000 | Honeywell Limit Switch #BZE6-2RN2 | 147.34 | 147.34 | 0
[5 empty] | 110000 | Greystone Outside Ambient Air Temp. Trans. | 237.65 | 237.65 | 0
[5 empty] | 130000 | Temp. Transmitter #YTA110-EA2DN/FU1/D2 | 681.03 | 681.03 | 0
[5 empty] | 140000 | Temperature Sensor with Thermowell | 280.18 | 280.18 | 0
[5 empty] | 160000 | Estimated Shipping | 358.4 | 358.4 | 0
|  |  | PO-103701 Total |  |  |  | 5977.49 | 5977.49 | 0
|  |  | PO-103511 | GE Intelligent Platforms | 10000 | I/O Filler Module #IC200ACC301 | 23.4 | 23.4 | 0
[5 empty] | 20000 | I/O Shorting Bar QTY2 #IC200ACC303 | 33.6 | 33.6 | 0
[5 empty] | 30000 | Analog input 16 bit voltage/current 8 isolated ch. | 2155.2 | 2155.2 | 0
[5 empty] | 50000 | Compact I/O carrier box style#IC200CHS022 | 456 | 456 | 0
[5 empty] | 60000 | CPU 128K User Config. User Memory #IC200CPUE05 | 783.6 | 783.6 | 0
[5 empty] | 70000 | Input 24VDC POS/NEG Logic 16 Points#IC200MDL640 | 87 | 87 | 0
[5 empty] | 80000 | Output 12/24VDC POS Logic 16 Point#IC200MDL740 | 176.4 | 176.4 | 0
[5 empty] | 90000 | Power Supply w/ Expanded 3.3VDC 24 VDC Input | 39 | 39 | 0
[5 empty] | 110000 | View Intermediate 6" STN Touch DC #IC754VSI06STD | 1576.5 | 1576.5 | 0
[5 empty] | 120000 | Shipping Estimated | 306.89 | 306.89 | 0
[5 empty] | 138750 | Analog input 16 bit voltage/current 8 isolated ch. | -1077.6 | -1077.6 | 0
[5 empty] | 139687 | Compact I/O carrier box style#IC200CHS022 | -228 | -228 | 0
[5 empty] | 139843 | CPU 128K User Config. User Memory #IC200CPUE05 | -783.6 | -783.6 | 0
[5 empty] | 139896 | CPU 128K User Config. User Memory #IC200CPUE05 | 783.6 | 783.6 | 0
[5 empty] | 139950 | Output 12/24VDC POS Logic 16 Point#IC200MDL740 | -88.2 | -88.2 | 0
[5 empty] | 139995 | View Intermediate 6" STN Touch DC #IC754VSI06STD | -788.25 | -788.25 | 0
[5 empty] | 139997 | Shipping Estimated | -223.79 | -223.79 | 0
|  |  | PO-103511 Total |  |  |  | 3231.75 | 3231.75 | 0
J101396 Total | [6 empty] | 261729.5 | 117975.93 | 143753.57
J101397 | Wily Splain | 2 | PO-103052 | Fosdick & Hilmer | 40000 | Professional Consulting Services for FWA 336A | 10020.83 | 10020.83 | 0
|  |  | PO-103052 Total |  |  |  | 10020.83 | 10020.83 | 0
|  |  | PO-103776 | Vertex | 20000 | 6" DIP w/3" polyurethane foam | 3581.4 | 3581.4 | 0
|  |  | PO-103776 Total |  |  |  | 3581.4 | 3581.4 | 0
|  |  | PO-104026 | Paragon General Construction | 30000 | Quality Assurance for 336A Aircraft Storage | 6666.66 | 1362.51 | 5304.15
|  |  | PO-104026 Total |  |  |  | 6666.66 | 1362.51 | 5304.15
|  |  | PO-104343 | Fosdick & Hilmer | 30000 | Construction Consulting for FTW 336A | 8840 | 3536 | 5304
[5 empty] | 49687 | Construction Consulting for FTW 336A | 4420 | 4420 | 0
|  |  | PO-104343 Total |  |  |  | 13260 | 7956 | 5304
|  |  | PO-103647 | Ferguson Enterprise Inc. | 450000 | 6 DI PIPE CL50 TYTON JT | 4824.22 | 4824.22 | 0
[5 empty] | 460000 | 6 MJ C153 90 Bend L/A | 241.42 | 241.42 | 0
[5 empty] | 470000 | 6 MJ C153 45 Bend L/A | 419.8 | 419.8 | 0
[5 empty] | 480000 | 8X5 DI TRANS COUP 9.06-9.06 | 324.2 | 324.2 | 0
[5 empty] | 490000 | 6 MJ C153 ACC PK | 716.69 | 716.69 | 0
[5 empty] | 500000 | 8 MJ C153 ACC PK | 38.84 | 38.84 | 0
[5 empty] | 510000 | 6 MJ C153 SLD CAP L/A | 116.49 | 116.49 | 0
[5 empty] | 520000 | 6 MJ C153 WYE L/A | 840.36 | 840.36 | 0
[5 empty] | 530000 | 8X6 MJ C153 WYE L/A | 185.47 | 185.47 | 0
|  |  | PO-103647 Total |  |  |  | 7707.49 | 7707.49 | 0
J101397 Total | [6 empty] | 41236.38 | 30628.23 | 10608.15
Grand Total | [6 empty] | 1010638.73 | 659357.53 | 351281.2

## JobDetail
Job No_ | Project Manager | Status | Posting Date | Order No_ | Buy-from Vendor Name | External Document No_ | No_ | Description | Job Task No_ | Total
J101394 | Bill Farrell | 2 | 2009-11-17 | PO-103052 | Fosdick & Hilmer | 11141 | 10501 | Professional Consulting Services for FWA 336A | EDS 364 4 | 6937.5
|  |  | 2010-02-01 | PO-103267 | Dryden & Larue Inc. | 9954 | 10501 | Design & Engineering Support | EDS 369 4 | 1731.4
|  |  | 2010-02-28 | (blank) | (blank) |  | 10501 | Recl Fosdick & Hilmer frm J101394 to J101395/6/7 | EDS 364 4 | -6937.5
|  |  | 2010-04-28 | PO-103267 | Dryden & Larue Inc. | 10399 | 10501 | Design & Engineering Support | EDS 369 4 | 1312.18
|  |  | 2010-04-30 | PO-103349 | Riddle Consulting, Inc. | APRIL 2010 | 10501 | Open PO for Riddle Consulting for 2010 Year | EDS 364 4 | 380.18
|  |  | 2010-05-01 | PO-103267 | Dryden & Larue Inc. | 10533 | 10501 | Design & Engineering Support | EDS 369 4 | 1968
|  |  |  | PO-103349 | Riddle Consulting, Inc. | MAY 2010 | 10501 | Open PO for Riddle Consulting for 2010 Year | EDS 364 4 | 328.33
|  |  | 2010-05-20 | PO-103551 | Fairbanks Precast & Rebar | 2730 | 10501 | SUM 1-B for New EDS Utility Service for FTW 336A | EDS 364 4 | 1095
|  |  | 2010-06-01 | PO-103267 | Dryden & Larue Inc. | 10752 | 10501 | Design & Engineering Support | EDS 369 4 | 384
|  |  | 2010-06-21 | PO-103691 | Potelcom Supply | 0021434-IN | 10501 | #12 CU 600V, XHHW Black | EDS 364 4 | 125
[8 empty] | #12 CU 600V, XHHW Green | EDS 364 4 | 125
[8 empty] | #12 CU 600V, XHHW White | EDS 364 4 | 125
[8 empty] | #2 SECONDARY QUADRUPLEX AL UNDERGROUND | EDS 364 4 | 151.5
[8 empty] | #4 XHHW, 600V | EDS 364 4 | 250
[8 empty] | 1/0 CONC 15kV AL, FULL NEUTRAL, 133% INSULATION | EDS 364 4 | 550
[8 empty] | 1PH OVERHEAD CONVENTIONAL TRANSFORMER (50 kVA) | EDS 364 4 | 1849.33
[8 empty] | 250kcmil XHHW, 600V | EDS 364 4 | 787.5
[8 empty] | 3PH CABLE TERM. POLE DEADEND W/CUTOUTS & ARRESTERS | EDS 364 4 | 1496.97
[8 empty] | 3PH PAD MOUNTED TRANS. LOOP FEED W/RADIAL 300 kVA | EDS 364 4 | 465.63
[8 empty] | CONDUIT, 1" HDPE - SCHEDULE 40 | EDS 364 4 | 212.4
[8 empty] | CONDUIT, 2" GALVANIZED RIGID STEEL | EDS 364 4 | 159.6
[8 empty] | CONDUIT, 2" HDPE - SCHEDULE 40 | EDS 364 4 | 80
[8 empty] | CONDUIT, 2.5" GALVANIZED RIGID STEEL | EDS 364 4 | 924
[8 empty] | CONDUIT, 4" GALVANIZED RIGID STEEL | EDS 364 4 | 413.1
[8 empty] | CONDUIT, 4" HDPE - SCHEDULE 40 | EDS 364 4 | 165.6
[8 empty] | ELBOW CONDUIT 2.5" RIGID STEEL SHORT SWEEP 90°18"R | EDS 364 4 | 90
[8 empty] | ELBOW CONDUIT 4" RIGID STEEL SHORT SWEEP 90° 36"R | EDS 364 4 | 223.3
[8 empty] | ELBOW, CONDUIT 2" RIGID STEEL SHORT SWEEP 90°24"R | EDS 364 4 | 36.55
[8 empty] | GROUND ROD ASSEMBLY | EDS 364 4 | 14.69
[8 empty] | GROUNDING ASSEMBLY - GROUND ROD TYPE | EDS 364 4 | 54.81
[8 empty] | LOAD BREAK ELBOW (200A) | EDS 364 4 | 140.85
[8 empty] | SECONDARY CABLE TERMINAL POLE | EDS 364 4 | 281.45
|  |  |  | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 364 4 | 38.66
|  |  | 2010-06-30 | PO-103349 | Riddle Consulting, Inc. | JUNE 2010 | 10501 | Open PO for Riddle Consulting for 2010 Year | EDS 364 4 | 330.43
|  |  |  | (blank) | (blank) |  | 10501 | Overhead:J101394 EDS 364 4 | EDS 364 4 | 59.28
[7 empty] | EMP120 | Salary - Hours | EDS 364 4 | 38.66
|  |  | 2010-07-01 | PO-103267 | Dryden & Larue Inc. | 10884 | 10501 | Design & Engineering Support | EDS 369 4 | 210.5
|  |  | 2010-07-07 | PO-103507 | Potelcom Supply | 0021817-IN | 10501 | 300kVA 12470/480 Y: Y Padmount | EDS 364 4 | 10546
|  |  | 2010-07-12 | PO-103691 | Potelcom Supply | 0021933-IN | 10501 | 30' Steel Pole | EDS 364 4 | 5780
|  |  | 2010-07-19 | PO-103691 | Potelcom Supply | 0022120-IN | 10501 | 400A SERVICE STD BREAKER CT-CAN METER SOCKET | EDS 364 4 | 4027
[8 empty] | ELBOW, CONDUIT 2" RIGID STEEL SHORT SWEEP 90°24"R | EDS 364 4 | 36.55
|  |  | 2010-07-22 | PO-103730 | Fullford Electric, Inc. | 2010286 | 10501 | Labor to Construct FTW336A Aircraft Parts Storage | EDS 364 4 | 12698
|  |  | 2010-07-26 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 364 4 | 38.66
[7 empty] | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-07-27 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-07-28 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 364 4 | 38.66
[7 empty] | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-07-29 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-07-30 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-07-31 | PO-103349 | Riddle Consulting, Inc. | JULY 2010 | 10501 | Open PO for Riddle Consulting for 2010 Year | EDS 364 4 | 142.16
|  |  |  | (blank) | (blank) |  | 10501 | Overhead:J101394 EDS 364 4 | EDS 364 4 | 155.12
|  |  | 2010-08-02 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 364 4 | 38.66
|  |  | 2010-08-04 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 364 4 | 38.66
|  |  | 2010-08-05 | PO-103691 | Potelcom Supply | 0022590-IN | 10501 | #2/0 XHHW, 600V | EDS 364 4 | 2710
[8 empty] | 100A 240V SITE LIGHTING LOAD CENTER | EDS 364 4 | 4041.63
|  |  | 2010-08-09 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 364 4 | 38.66
|  |  | 2010-08-10 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-08-16 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-08-17 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-08-18 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-08-19 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-08-23 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-08-24 | PO-103730 | Fullford Electric, Inc. | 2010350 | 10501 | Labor to Construct FTW336A Aircraft Parts Storage | EDS 364 4 | 12698
|  |  |  | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-08-25 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-08-26 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-08-27 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 19.33
|  |  | 2010-08-30 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 369 4 | 25
|  |  | 2010-08-31 | PO-103349 | Riddle Consulting, Inc. | AUGUST2010 | 10501 | Open PO for Riddle Consulting for 2010 Year | EDS 364 4 | 191.11
|  |  |  | (blank) | (blank) |  | 10501 | Inv # 10302 - Meter,Electric 2s | EDS 364 4 | 136.02
[8 empty] | Overhead:J101394 EDS 364 4 | EDS 364 4 | 88.92
[8 empty] | Overhead:J101394 EDS 366 4 | EDS 366 4 | 95.84
[8 empty] | Overhead:J101394 EDS 369 4 | EDS 369 4 | 14.82
[8 empty] | Overhead:J101394 EDS 370 4 | EDS 368 4 | 76.67
[7 empty] | EMP159 | Bracketed Hourly Pay | EDS 369 4 | 25
|  |  | 2010-09-01 | PO-103267 | Dryden & Larue Inc. | 11263 | 10501 | Design & Engineering Support | EDS 369 4 | 5416.12
|  |  |  | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 369 4 | 25
|  |  | 2010-09-02 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 369 4 | 25
|  |  | 2010-09-03 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 19.33
|  |  | 2010-09-07 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-09-08 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-09-09 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-09-13 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-09-15 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-09-16 | PO-104016 | North Coast Electric | S3594559.001 | 10501 | Misc. Materials for 336A Aircraft Part Facility | EDS 369 4 | 697.96
|  |  |  | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
[6 empty] | CMS3594610.001 | 10501 | CM/ RETURN OF BREAKER | EDS 369 4 | -33.16
|  |  | 2010-09-17 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-09-20 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 365 4 | 25
|  |  | 2010-09-21 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 365 4 | 25
|  |  | 2010-09-22 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 365 4 | 25
|  |  | 2010-09-23 | PO-103730 | Fullford Electric, Inc. | 2010410 | 10501 | Labor to Construct FTW336A Aircraft Parts Storage | EDS 364 4 | 22221.5
|  |  |  | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 365 4 | 25
|  |  | 2010-09-27 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 369 4 | 25
|  |  | 2010-09-28 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 369 4 | 25
|  |  | 2010-09-29 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 369 4 | 25
|  |  | 2010-09-30 | PO-103349 | Riddle Consulting, Inc. | SEPTEMBER2010 | 10501 | Open PO for Riddle Consulting for 2010 Year | EDS 364 4 | 238.19
|  |  |  | (blank) | (blank) |  | 10501 | Overhead:J101394 EDS 365 4 | EDS 365 4 | 76.67
[8 empty] | Overhead:J101394 EDS 366 4 | EDS 366 4 | 76.67
[8 empty] | Overhead:J101394 EDS 368 4 | EDS 368 4 | 57.5
[8 empty] | Overhead:J101394 EDS 369 4 | EDS 369 4 | 91.49
[7 empty] | EMP159 | Bracketed Hourly Pay | EDS 369 4 | 25
|  |  | 2010-10-01 | PO-103267 | Dryden & Larue Inc. | 11263A | 10501 | Correction for receipting error | EDS 364 4 | -1503.5
[8 empty] | Design & Engineering Support | EDS 369 4 | 1503.5
|  |  |  | PO-104016 | North Coast Electric | S3591060.001 | 10501 | Misc. Materials for 336A Aircraft Part Facility | EDS 369 4 | 720.08
|  |  | 2010-10-04 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-05 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-06 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-07 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-08 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 38.66
|  |  | 2010-10-11 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-12 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-13 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-14 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-15 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 38.66
|  |  | 2010-10-18 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 38.66
[7 empty] | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-19 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 38.66
[7 empty] | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-20 | PO-103730 | Fullford Electric, Inc. | 2010445 | 10501 | Labor to Construct FTW336A Aircraft Parts Storage | EDS 364 4 | 15872.5
|  |  |  | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-21 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 57.99
[7 empty] | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-10-22 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 38.66
|  |  | 2010-10-25 | PO-104016 | North Coast Electric | S3654668.001 | 10501 | Misc. Materials for 336A Aircraft Part Facility | EDS 369 4 | 590.95
[6 empty] | S3655733.001 | 10501 | Misc. Materials for 336A Aircraft Part Facility | EDS 369 4 | 60.72
|  |  |  | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 38.66
|  |  | 2010-10-26 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 38.66
|  |  | 2010-10-29 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 38.66
|  |  | 2010-10-31 | PO-103349 | Riddle Consulting, Inc. | OCTOBER 2010 | 10501 | Open PO for Riddle Consulting for 2010 Year | EDS 364 4 | 263.37
|  |  |  | (blank) | (blank) |  | 10501 | Overhead:J101394 EDS 364 4 | EDS 364 4 | 230.01
[8 empty] | Overhead:J101394 EDS 369 4 | EDS 369 4 | 358.25
|  |  | 2010-11-03 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-11-01 | PO-103267 | Dryden & Larue Inc. | 11605 | 10501 | Correction for receipting error | EDS 364 4 | 1503.5
[8 empty] | Design & Engineering Support | EDS 369 4 | 1249.62
|  |  |  | PO-104016 | North Coast Electric | S3654668.002 | 10501 | Misc. Materials for 336A Aircraft Part Facility | EDS 369 4 | 2162.56
|  |  | 2010-11-04 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-11-16 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-11-02 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 366 4 | 25
|  |  | 2010-11-17 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-11-18 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-11-15 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 368 4 | 25
|  |  | 2010-11-10 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-11-09 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-11-08 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 38.66
[7 empty] | EMP159 | Bracketed Hourly Pay | EDS 364 4 | 25
|  |  | 2010-11-30 | PO-103349 | Riddle Consulting, Inc. | NOVEMBER 2010 | 10501 | Open PO for Riddle Consulting for 2010 Year | EDS 364 4 | 88.48
|  |  |  | (blank) | (blank) |  | 10501 | Overhead:J101394 EDS 364 4 | EDS 364 4 | 57.5
[8 empty] | Overhead:J101394 EDS 366 4 | EDS 366 4 | 57.5
[8 empty] | Overhead:J101394 EDS 368 4 | EDS 368 4 | 76.67
[8 empty] | Overhead:J101394 EDS 369 4 | EDS 369 4 | 29.64
[8 empty] | Inv #10304 - Meter, Electric 16s - 1ea | EDS 369 4 | 453.62
[8 empty] | Inv #10313 - Meter, Electric 9s - 1ea | EDS 369 4 | 837.83
[8 empty] | Inv #10302 - Meter,Electric 2s - 1ea | EDS 369 4 | 136.02
|  |  | 2010-12-02 | (blank) | (blank) |  | EMP120 | Salary - Hours | EDS 369 4 | 77.32
|  |  | 2010-12-01 | PO-103267 | Dryden & Larue Inc. | 11826 | 10501 | Design & Engineering Support | EDS 369 4 | 2616.63
|  |  |  | PO-103730 | Fullford Electric, Inc. | 2010481 | 10501 | CO # 1 - Material and Labor for Light Pole Bases | EDS 364 4 | 4748.22
|  |  | 2010-12-31 | PO-103349 | Riddle Consulting, Inc. | DECEMBER 2010 | 10501 | Open PO for Riddle Consulting for 2010 Year | EDS 364 4 | 87.5
|  |  |  | (blank) | (blank) |  | 10501 | Overhead:J101394 EDS 369 4 | EDS 369 4 | 59.28
J101394 Total | [9 empty] | 133230.34
J101395 | Wily Splain | 2 | 2009-11-17 | PO-103052 | Fosdick & Hilmer | 11141 | 10501 | Professional Consulting Services for FWA 336A | DHS 231 4.2 | 6937.5
|  |  | 2010-02-28 | (blank) | (blank) |  | 10501 | Recl Fosdick & Hilmer frm J101394 to J101395/6/7 | DHS 231 4.2 | 2312.5
|  |  | 2010-05-10 | PO-103052 | Fosdick & Hilmer | 11597 | 10501 | Professional Consulting Services for FWA 336A | DHS 231 4.2 | 3083.34
|  |  | 2010-06-04 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 184.6
|  |  | 2010-06-08 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 184.6
|  |  | 2010-06-11 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-06-15 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 184.6
|  |  | 2010-06-18 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-06-21 | PO-103639 | Maynard Reece | 0000047505 | 10501 | Plate Conditioner 35 Hole 3" #DK7ST-80K0 | DHS 232 4.2 | 590
[8 empty] | Prowil 3" Steam Meter #73F80-SK4AA1NAB4AA | DHS 232 4.2 | 4935
|  |  | 2010-06-22 | PO-103653 | Badger Meter | 55894701 | 10501 | Model 350T Transmitter for Steam Meters, 20' Lead | DHS 232 4.2 | 210
[8 empty] | Shipping Charges | DHS 232 4.2 | 57.28
|  |  |  | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-06-24 | PO-103647 | Ferguson Enterprise Inc. | 0953877 | 10501 | 1 SS 316L 3000# SOC 45 ELL | DHS 232 4.2 | 55.95
[8 empty] | 1 SS 316L 3000# SOC 90 ELL | DHS 232 4.2 | 110.57
[8 empty] | 1 SS 316L 3000# SOC COUP | DHS 232 4.2 | 28.04
[8 empty] | 1 SS 316L 3000# SOC UNION | DHS 232 4.2 | 25.48
[8 empty] | 1 SS SCH10 316L A312 WELD PIPE | DHS 232 4.2 | 498.9
[8 empty] | 1-1/2 FS 3000# SOC COUP | DHS 232 4.2 | 17.01
[8 empty] | 1-1/2 IMP BLK PE A106B 40 SMLS SRL | DHS 232 4.2 | 53.58
[8 empty] | 1-1/2 SS 316L 3000# SOC 45 ELL | DHS 232 4.2 | 221.81
[8 empty] | 1-1/2 SS 316L 3000# SOC 90 ELL | DHS 232 4.2 | 565.25
[8 empty] | 1-1/2 SS 316L 3000# SOC COUP | DHS 232 4.2 | 146.67
[8 empty] | 1-1/2 SS SCH10 316L A312 WELD PIPE | DHS 232 4.2 | 714.3
[8 empty] | 1-1/2 VELAN 800# SW SS SWING CHK VL | DHS 232 4.2 | 1492.58
[8 empty] | 1X12 SS FLEX W/ SS SW ENDS | DHS 232 4.2 | 111.92
[8 empty] | 2 FS 3000# SOC 90 ELL | DHS 232 4.2 | 41.78
[8 empty] | 2 FS 3000# SOC COUP | DHS 232 4.2 | 16.32
[8 empty] | 2 FS 3000# SOC STL STL UNION | DHS 232 4.2 | 35.87
[8 empty] | 2 FS 3000# SOC TEE | DHS 232 4.2 | 28.71
[8 empty] | 2 IMP BLK PE A106B 40 SMLS SRL | DHS 232 4.2 | 69.73
[8 empty] | 2 VELAN 800# SW CS SWING CHK VLV | DHS 232 4.2 | 287.89
[8 empty] | 2X2X3/4 FS 3000# SOC TEE | DHS 232 4.2 | 56.97
[8 empty] | 2X3/4 FS 3000# SOC RED | DHS 232 4.2 | 36.89
[8 empty] | 3 CS STD WELD 45 ELL | DHS 232 4.2 | 47.7
[8 empty] | 3 CS STD WELD CAP | DHS 232 4.2 | 16.1
[8 empty] | 3 CS STD WELD LR 90 ELL | DHS 232 4.2 | 155.85
[8 empty] | 3 CS STD WELD TEE | DHS 232 4.2 | 87.5
[8 empty] | 3 IMP BLK PE A106B 40 SMLS SRL | DHS 232 4.2 | 1732.95
[8 empty] | 3 VELAN 150# BW CS FP GATE VLV | DHS 232 4.2 | 1077.53
[8 empty] | 3/4 CS 600# SW PERF Y STRN | DHS 232 4.2 | 247.39
[8 empty] | 3/4 FS 3000# SOC COUP | DHS 232 4.2 | 6.26
[8 empty] | 3/4 FS 3000# SOC STL STL UNION | DHS 232 4.2 | 11
[8 empty] | 3/4 IMP BLK PE A106B 40 SMLS SRL | DHS 232 4.2 | 25.12
[8 empty] | 3/4 SS 316L 3000# SOC 45 ELL | DHS 232 4.2 | 92.65
[8 empty] | 3/4 SS 316L 3000# SOC 90 ELL | DHS 232 4.2 | 148.34
[8 empty] | 3/4 SS 316L 3000# SOC TEE | DHS 232 4.2 | 47.75
[8 empty] | 3/4 SS 316L 3000# SOC UNION | DHS 232 4.2 | 63.35
[8 empty] | 3/4 TD-52 STM TRAP | DHS 232 4.2 | 1175.76
[8 empty] | 3/4 VELAN 800# SW SS SWING CHK VLV | DHS 232 4.2 | 3132.97
[8 empty] | 3/4X12 SS FLEX W/ SS SW ENDS | DHS 232 4.2 | 363.95
[8 empty] | 3X2 CS STD WELD ECC RED | DHS 232 4.2 | 20.77
|  |  | 2010-06-25 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-06-28 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 184.6
|  |  | 2010-06-29 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 138.45
|  |  | 2010-06-30 | (blank) | (blank) |  | 10501 | Overhead:J101395 DHS 231 4.2 | DHS 231 4.2 | 990.73
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-07-05 |  | Travis / Peterson | 6154 | 10501 | FWA GLOBAL SAP | DHS 232 4.2 | 2250
|  |  | 2010-07-07 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-07-15 | PO-103576 | Perma-Pipe | PPR19904 | 10501 | Direct Bury Pipe for 336A | DHS 232 4.2 | 3341
|  |  | 2010-07-26 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | DHS 231 4.2 | 25
|  |  | 2010-07-27 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | DHS 231 4.2 | 25
|  |  | 2010-07-28 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | DHS 231 4.2 | 25
|  |  | 2010-07-29 | PO-103647 | Ferguson Enterprise Inc. | 0953877-1 | 10501 | 1 APOLLO 600# SW FP CS BALL VLV | DHS 232 4.2 | 289.34
[8 empty] | 1-1/2 APOLLO 600# SW FP CS BALL VLV | DHS 232 4.2 | 2745.38
[8 empty] | 2 APOLLO 600# SW FP CS BALL VLV | DHS 232 4.2 | 998.68
[8 empty] | 3 CS STD WELD 45 ELL | DHS 232 4.2 | 33.39
[8 empty] | 3 CS STD WELD LR 90 ELL | DHS 232 4.2 | 93.51
[8 empty] | 3/4 APOLLO 600# SW FP CS BALL VLV | DHS 232 4.2 | 2492.52
[8 empty] | 3/4 FS 3000# SOC STL STL UNION | DHS 232 4.2 | 11
[6 empty] | 0968049 | 10501 | 1-1/2 IMP BLK PE A106B 40 SMLS SRL | DHS 232 4.2 | 8.04
[8 empty] | 3 IMP BLK PE A106B 40 SMLS SRL | DHS 232 4.2 | 92.65
[8 empty] | 3/4 IMP BLK PE A106B 40 SMLS SRL | DHS 232 4.2 | 3.77
[8 empty] | 6 BLK PE A106B 40 SMLS SRL PIPE | DHS 232 4.2 | 56.97
|  |  |  | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | DHS 231 4.2 | 25
|  |  | 2010-07-30 | PO-103647 | Ferguson Enterprise Inc. | 0953877-2 | 10501 | 1-1/2 APOLLO 600# SW FP CS BALL VLV | DHS 232 4.2 | 795.56
[8 empty] | 1-1/2 SS SCH10 316L A312 WELD PIPE | DHS 232 4.2 | 1000.02
[8 empty] | 3/4 SS SCH10 316L A312 WELD PIPE | DHS 232 4.2 | 131.44
|  |  |  | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | DHS 231 4.2 | 25
|  |  | 2010-07-31 | (blank) | (blank) |  | 10501 | Overhead:J101395 DHS 231 4.2 | DHS 231 4.2 | 166.61
|  |  | 2010-08-02 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 74.78
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-08-03 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-08-04 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 74.78
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-08-06 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 74.78
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-08-07 | PO-103576 | Perma-Pipe | PPR20012A | 10501 | Direct Bury Pipe for 336A | DHS 232 4.2 | 0
[8 empty] | Expedited Shipping | DHS 232 4.2 | 0
|  |  | 2010-08-11 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-08-12 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 74.78
|  |  | 2010-08-16 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 149.56
|  |  | 2010-08-18 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-08-19 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-08-21 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 082110 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 242
|  |  | 2010-08-25 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-08-26 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-08-27 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-08-30 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-08-31 | (blank) | (blank) |  | 10501 | Overhead:J101395 DHS 231 4.2 | DHS 231 4.2 | 803.98
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-01 |  | Tunista Arctic Rim/TBI Const | PE-01 | 10501 | INSTALL UTILITIESTO FTW336A AIRCRAFT STORAGE | DHS 232 4.2 | 133486
|  |  |  | PO-104026 | Paragon General Construction | 336A AIRCRAFT 083110 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 80.53
|  |  |  | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-09-02 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-03 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-04 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 090410 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 143.54
|  |  | 2010-09-07 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-08 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-09 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-10 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-11 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 091110 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 98.21
|  |  | 2010-09-13 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-14 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-15 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 149.56
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-16 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 149.56
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-17 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 299.12
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-20 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-21 | PO-104343 | Fosdick & Hilmer | 11932 | 10501 | Construction Consulting for FTW 336A | DHS 231 4.2 | 4420
|  |  |  | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 149.56
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-22 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 149.56
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-23 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-24 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-25 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 092510 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 340.31
|  |  | 2010-09-27 | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 74.78
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-28 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-09-29 |  | CB Engineering Pacific Inc. | IP91085983 | 10501 | MULTI-LEVEL SWITCH | DHS 232 4.2 | 280.7
|  |  |  | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 74.78
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-09-30 | (blank) | (blank) |  | 10501 | Overhead:J101395 DHS 231 4.2 | DHS 231 4.2 | 1395.67
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-01 | PO-103576 | Perma-Pipe | PPR20283 | 10501 | Direct Bury Pipe for 336A | DHS 232 4.2 | 16802
[8 empty] | Expedited Shipping | DHS 232 4.2 | 4282
|  |  |  | PO-104026 | Paragon General Construction | 002 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 206.46
[6 empty] | 011 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 63.08
[6 empty] | 038 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 45.38
|  |  |  | (blank) | (blank) |  | EMP114 | Salary - Hours | DHS 231 4.2 | 74.78
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-04 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-05 | (blank) | (blank) |  | EMP042 | Salary - Hours | DHS 232 4.2 | 48.55
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-06 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-07 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-08 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-11 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-12 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-13 | PO-103909 | Tunista Arctic Rim/TBI Const. | PE-02 | 10501 | Utilidor and Direct Buried HDS Mains | DHS 231 4.2 | 53142
[8 empty] | Utilidors and Access Vaults | DHS 231 4.2 | 250387.25
|  |  |  | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-14 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-15 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-17 | PO-104026 | Paragon General Construction | 020 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 244.8
|  |  | 2010-10-18 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-19 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-20 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-21 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-22 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-24 | PO-104026 | Paragon General Construction | 029 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 103.23
|  |  | 2010-10-25 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-26 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-27 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-28 | (blank) | (blank) |  | EMP159 | Bracketed Hourly Pay | DHS 232 4.2 | 25
[7 empty] | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-10-29 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-10-31 | (blank) | (blank) |  | 10501 | Overhead:J101395 DHS 231 4.2 | DHS 231 4.2 | 1481.18
[8 empty] | Overhead:J101395 DHS 232 4.2 | DHS 232 4.2 | 56.39
|  |  | 2010-11-03 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-05 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-01 | PO-104026 | Paragon General Construction | 070 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 89.37
|  |  | 2010-11-04 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-16 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-02 | PO-104343 | Fosdick & Hilmer | 12031 | 10501 | Construction Consulting for FTW 336A | DHS 231 4.2 | 3536
|  |  |  | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-17 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-18 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-11-15 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-12 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-10 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-09 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-08 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-11-30 | (blank) | (blank) |  | 10501 | Overhead:J101395 DHS 231 4.2 | DHS 231 4.2 | 459.98
|  |  | 2010-12-08 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 184.6
|  |  | 2010-12-09 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 184.6
|  |  | 2010-12-01 | PO-104026 | Paragon General Construction | 101 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 19.45
[6 empty] | 10022010-104026 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 508.2
[6 empty] | 09182010 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 166.21
[6 empty] | 088 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 43.66
|  |  | 2010-11-14 | PO-104026 | Paragon General Construction | 079 | 10501 | Quality Assurance for 336A Aircraft Storage | DHS 231 4.2 | 5.99
|  |  | 2010-12-15 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-12-13 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
|  |  | 2010-12-16 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 92.3
|  |  | 2010-12-31 | (blank) | (blank) |  | 10501 | Overhead:J101395 DHS 231 4.2 | DHS 231 4.2 | 495.36
|  |  | 2010-12-14 | (blank) | (blank) |  | EMP162 | Salary - Hours | DHS 231 4.2 | 46.15
J101395 Total | [9 empty] | 527754.3
J101396 | Wily Splain | 2 | 2009-11-17 | PO-103052 | Fosdick & Hilmer | 11141 | 10501 | Professional Consulting Services for FWA 336A | WTD 331 4 | 6937.5
|  |  | 2010-02-28 | (blank) | (blank) |  | 10501 | Recl Fosdick & Hilmer frm J101394 to J101395/6/7 | WTD 331 4 | 2312.5
|  |  | 2010-04-02 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 392.24
|  |  | 2010-04-06 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-04-09 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 294.18
|  |  | 2010-04-12 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 49.03
|  |  | 2010-04-14 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-04-15 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-04-16 | PO-103511 | GE Intelligent Platforms | 71448486 | 10501 | Analog input 16 bit voltage/current 8 isolated ch. | WTD 331 4 | 0
[8 empty] | Compact I/O carrier box style#IC200CHS022 | WTD 331 4 | 0
[8 empty] | CPU 128K User Config. User Memory #IC200CPUE05 | WTD 331 4 | 0
[8 empty] | I/O Filler Module #IC200ACC301 | WTD 331 4 | 23.4
[8 empty] | I/O Shorting Bar QTY2 #IC200ACC303 | WTD 331 4 | 33.6
[8 empty] | Input 24VDC POS/NEG Logic 16 Points#IC200MDL640 | WTD 331 4 | 87
[8 empty] | Output 12/24VDC POS Logic 16 Point#IC200MDL740 | WTD 331 4 | 0
[8 empty] | Power Supply w/ Expanded 3.3VDC 24 VDC Input | WTD 331 4 | 39
[8 empty] | Shipping Estimated | WTD 331 4 | 26.21
[8 empty] | View Intermediate 6" STN Touch DC #IC754VSI06STD | WTD 331 4 | 0
|  |  |  | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-04-20 | PO-103511 | GE Intelligent Platforms | 71449262 | 10501 | Analog input 16 bit voltage/current 8 isolated ch. | WTD 331 4 | 1077.6
[8 empty] | Compact I/O carrier box style#IC200CHS022 | WTD 331 4 | 228
[8 empty] | Output 12/24VDC POS Logic 16 Point#IC200MDL740 | WTD 331 4 | 88.2
[8 empty] | Shipping Estimated | WTD 331 4 | 31.3
[8 empty] | View Intermediate 6" STN Touch DC #IC754VSI06STD | WTD 331 4 | 788.25
|  |  | 2010-04-21 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-04-26 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-04-27 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-04-28 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-04-29 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-04-30 | (blank) | (blank) |  | 10501 | Overhead:J101396 WTD 331 4 | WTD 331 4 | 1240.51
|  |  | 2010-05-03 | PO-103511 | GE Intelligent Platforms | 71452265 | 10501 | CPU 128K User Config. User Memory #IC200CPUE05 | WTD 331 4 | 783.6
[8 empty] | Shipping Estimated | WTD 331 4 | 25.59
|  |  | 2010-05-05 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-05-10 | PO-103052 | Fosdick & Hilmer | 11597 | 10501 | Professional Consulting Services for FWA 336A | WTD 331 4 | 3083.33
|  |  |  | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-05-12 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-05-13 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 196.12
|  |  | 2010-05-17 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-05-24 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-05-25 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-05-26 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-05-27 | (blank) | (blank) |  | EMP007 | Salary - Hours | WTD 331 4 | 98.06
|  |  | 2010-05-31 | (blank) | (blank) |  | 10501 | Overhead:J101396 WTD 331 4 | WTD 331 4 | 751.83
|  |  | 2010-06-24 | PO-103647 | Ferguson Enterprise Inc. | 0953877 | 10501 | 1 BOT SECT F/ VB | WTD 331 4 | 33.9
[8 empty] | 1 FLR 90 BEND | WTD 331 4 | 67.14
[8 empty] | 1 FLR X MIP COUP | WTD 331 4 | 42.59
[8 empty] | 18 TOP SECTION F/ VB | WTD 331 4 | 30.22
[8 empty] | 1X100 K SOFT COP TUBE | WTD 331 4 | 588.79
[8 empty] | 2 BRS 600# WOG SWT 2PC FP BV | WTD 331 4 | 366.27
[8 empty] | 2 BRZ 150# THRD 20 MESH Y STRN | WTD 331 4 | 83.56
[8 empty] | 2 COP FLG ADPT GSKT 641 | WTD 331 4 | 1283.72
[8 empty] | 2 COP GRV 90 ELL 610 | WTD 331 4 | 371.4
[8 empty] | 2 RIGID COUP F/ COP TUBE 607 | WTD 331 4 | 699.89
[8 empty] | 2 X 20 L HARD COP TUBE (includes groove fee) | WTD 331 4 | 2703.05
[8 empty] | 2X3/4 COP GRV X COP TEE 626 | WTD 331 4 | 61.65
[8 empty] | 3/4 BRS 600# WOG SWT 2PC FP BV | WTD 331 4 | 10.2
[8 empty] | 4 PTD TRANS COUP FS M GSKT 307 | WTD 331 4 | 129.75
[8 empty] | 4X2 PTD GRV CONC RED 50 | WTD 331 4 | 51.33
[8 empty] | 4X5X53 STL HYD MRKR W/ POLY FLAG | WTD 331 4 | 32.42
[8 empty] | 5-1/4 BURY HYD 5'0 16 TRAFFIC 6 FLG | WTD 331 4 | 1922.18
[8 empty] | 5X5 SV SH SOIL PIPE | WTD 331 4 | 91.6
[8 empty] | 6 150# BOLT KIT 8 3/4X3-1/4 IMP | WTD 331 4 | 9.01
[8 empty] | 6 CL53 GRVXGRV DI PIPE | WTD 331 4 | 414.2
[8 empty] | 6 FLG RW OL GATE VLV W/ H/WHL ZN | WTD 331 4 | 519
[8 empty] | 6 FLG TYTE GSKT | WTD 331 4 | 11.43
[8 empty] | 6 MJ C153 ACC PK | WTD 331 4 | 15.17
[8 empty] | 6 MJ RW DI OL GATE VLV L/A | WTD 331 4 | 496.62
[8 empty] | 6 PTD GRV COUP F/ DIP 31 | WTD 331 4 | 232.58
[8 empty] | 6 ROMAGRIP ACCY PK F/ DI | WTD 331 4 | 573.28
[8 empty] | 8 45 ELL 11-C CDI CL T37-77 | WTD 331 4 | 291.64
[8 empty] | 8 CL53 GRVXGRV DI PIPE | WTD 331 4 | 1134.97
[8 empty] | 8 FLG RW OL GATE VLV W/ H/WHL ZN | WTD 331 4 | 1630.77
[8 empty] | 8 MJ C153 90 BEND L/A | WTD 331 4 | 107.49
[8 empty] | 8 PTD GRV COUP F/ DIP 31 | WTD 331 4 | 1886.96
[8 empty] | 8 ROMAGRIP ACCY PK F/ DI | WTD 331 4 | 442.96
[8 empty] | 8 TEE 20-C CDI CL T37-77 | WTD 331 4 | 198.8
[8 empty] | 8X6 MJ C153 SWVL TEE L/A | WTD 331 4 | 152.9
[8 empty] | PAVING SLV LID ONLY - WTR | WTD 331 4 | 10.48
[8 empty] | VLV BX DUST CUP | WTD 331 4 | 9.66
[6 empty] | 0964340 | 10501 | 6 DI PIPE CL50 TYTON JT | WTD 331 4 | 1152.24
[8 empty] | 8 DI PIPE CL50 TYTON JT | WTD 331 4 | 2609.12
|  |  | 2010-07-01 | PO-103653 | Badger Meter | 87748701 | 10501 | 2" Recordall M170 ELL, Bare,Low Lead Alloy Housing | WTD 331 4 | 464
[8 empty] | ADE and Orion Remote Module, 5/8"-2" Badger Disc | WTD 331 4 | 115
[8 empty] | Shipping Charges | WTD 331 4 | 91.04
|  |  | 2010-07-06 |  | Ferguson Enterprise Inc. | 0966813 | 10501 | CIRC PUMP | WTD 331 4 | 442.45
|  |  | 2010-07-19 | PO-103690 | Panel-Fab, Inc. | 1000883-IN | 10501 | Control Panel CP336AM | WTD 331 4 | 789
[8 empty] | Estimated Shipping | WTD 331 4 | 130
|  |  | 2010-07-29 | PO-103490 | Panel-Fab, Inc. | 1000942-IN | 10501 | Control Panel #CP-G693 | WTD 331 4 | 3748
[8 empty] | PLC & HMI Configuration and Programming provided | WTD 331 4 | 4200
[8 empty] | shipping | WTD 331 4 | 300
|  |  |  | PO-103647 | Ferguson Enterprise Inc. | 0953877-1 | 10501 | *CVR* 317 8 CKV 317 T37H-77 T SEAT | WTD 331 4 | 1638.18
[8 empty] | *CVR* A 8 90 LR ELL 100-C DI C/L T3 | WTD 331 4 | 896.4
[8 empty] | *CVR* A 8X6 CONC 50-C DI C/L T3 050 | WTD 331 4 | 206.34
[8 empty] | *CVR* A 8X8X4 RD TEE 25-C DI C/L T3 | WTD 331 4 | 451.33
[8 empty] | 2X1 COP GRV X COP TEE 626 | WTD 331 4 | 61.68
|  |  | 2010-08-01 | PO-103701 | CB Engineering Pacific Inc. | IP81085626 | 10501 | 12" Verabar Primary Flow Element | WTD 331 4 | 2012.9
[8 empty] | Differential Pressure Transmitter | WTD 331 4 | 989.45
[8 empty] | Direct Mount Gauge Pressure Transmitter | WTD 331 4 | 642.81
[8 empty] | Estimated Shipping | WTD 331 4 | 296
[8 empty] | Honeywell Limit Switch #BZE6-2RN2 | WTD 331 4 | 147.34
[8 empty] | Temp. Transmitter #YTA110-EA2DN/FU1/D2 | WTD 331 4 | 681.03
[8 empty] | Temperature Sensor with Thermowell | WTD 331 4 | 280.18
[8 empty] | Two Valve Manifold #PV-614SCG | WTD 331 4 | 237.92
|  |  | 2010-08-17 | PO-103776 | Vertex | 20222 | 10501 | 6" DIP w/3" polyurethane foam | WTD 331 4 | 855.4
[8 empty] | 8" DIP w/2" polyurethane foam | WTD 331 4 | 1529.45
|  |  | 2010-08-21 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 082110 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 242
|  |  | 2010-08-26 | PO-103701 | CB Engineering Pacific Inc. | IP810875747 | 10501 | Estimated Shipping | WTD 331 4 | 62.4
[8 empty] | Greystone Ambient air Temp. Trans.#TE500AS12GS003 | WTD 331 4 | 136.74
[8 empty] | Greystone Outside Ambient Air Temp. Trans. | WTD 331 4 | 237.65
[8 empty] | Greystone Temp/Humd Trans. #RH310A03C1A6 | WTD 331 4 | 253.07
|  |  | 2010-09-01 |  | Tunista Arctic Rim/TBI Const | PE-01 | 10501 | INSTALL UTILITIESTO FTW336A AIRCRAFT STORAGE | WTD 331 4 | 133486
|  |  |  | PO-104026 | Paragon General Construction | 336A AIRCRAFT 083110 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 80.54
|  |  | 2010-09-04 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 082810 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 318.53
[6 empty] | 336A AIRCRAFT 090410 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 143.55
|  |  | 2010-09-11 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 091110 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 98.22
|  |  | 2010-09-21 | PO-104343 | Fosdick & Hilmer | 11932 | 10501 | Construction Consulting for FTW 336A | WTD 331 4 | 4420
|  |  | 2010-10-01 | PO-104026 | Paragon General Construction | 002 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 111.17
[6 empty] | 011 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 63.08
|  |  | 2010-10-13 | PO-103909 | Tunista Arctic Rim/TBI Const. | PE-02 | 10501 | Utilidor and Direct Buried WDS Mains | WTD 331 4 | 53142
|  |  | 2010-10-17 | PO-104026 | Paragon General Construction | 020 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 131.81
|  |  | 2010-10-24 | PO-104026 | Paragon General Construction | 029 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 55.58
|  |  | 2010-11-01 | PO-104026 | Paragon General Construction | 070 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 48.12
|  |  | 2010-11-02 | PO-104343 | Fosdick & Hilmer | 12031 | 10501 | Construction Consulting for FTW 336A | WTD 331 4 | 3536
|  |  | 2010-12-01 | PO-104026 | Paragon General Construction | 10022010-104026 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 217.8
[6 empty] | 09182010 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 166.21
[6 empty] | 088 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 23.5
|  |  | 2010-11-14 | PO-104026 | Paragon General Construction | 079 | 10501 | Quality Assurance for 336A Aircraft Storage | WTD 331 4 | 2.99
J101396 Total | [9 empty] | 258807.81
J101397 | Wily Splain | 2 | 2009-11-17 | PO-103052 | Fosdick & Hilmer | 11141 | 10501 | Professional Consulting Services for FWA 336A | WWC 361 2 | 6937.5
|  |  | 2010-02-28 | (blank) | (blank) |  | 10501 | Recl Fosdick & Hilmer frm J101394 to J101395/6/7 | WWC 361 2 | 2312.5
|  |  | 2010-05-10 | PO-103052 | Fosdick & Hilmer | 11597 | 10501 | Professional Consulting Services for FWA 336A | WWC 361 2 | 3083.33
|  |  | 2010-06-24 | PO-103647 | Ferguson Enterprise Inc. | 0953877 | 10501 | 6 MJ C153 45 BEND L/A | WWC 361 2 | 419.8
[8 empty] | 6 MJ C153 90 BEND L/A | WWC 361 2 | 241.42
[8 empty] | 6 MJ C153 ACC PK | WWC 361 2 | 716.69
[8 empty] | 6 MJ C153 SLD CAP L/A | WWC 361 2 | 116.49
[8 empty] | 6 MJ C153 WYE L/A | WWC 361 2 | 840.36
[8 empty] | 8 MJ C153 ACC PK | WWC 361 2 | 38.84
[8 empty] | 8X5 DI TRANS COUP 9.06-9.06 | WWC 361 2 | 162.1
[8 empty] | 8X6 MJ C153 WYE L/A | WWC 361 2 | 185.47
[6 empty] | 0964340 | 10501 | 6 DI PIPE CL50 TYTON JT | WWC 361 2 | 4824.22
|  |  | 2010-07-29 | PO-103647 | Ferguson Enterprise Inc. | 0953877-1 | 10501 | 8X5 DI TRANS COUP 9.06-9.06 | WWC 361 2 | 162.1
|  |  | 2010-08-11 | (blank) | (blank) |  | EMP120 | Salary - Hours | WWC 361 2 | 38.66
|  |  | 2010-08-17 | PO-103776 | Vertex | 20222 | 10501 | 6" DIP w/3" polyurethane foam | WWC 361 2 | 3581.4
|  |  | 2010-08-21 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 082110 | 10501 | Quality Assurance for 336A Aircraft Storage | WWC 361 2 | 242
|  |  | 2010-08-31 | (blank) | (blank) |  | 10501 | Overhead:J101397 WWC 361 2 | WWC 361 2 | 29.64
|  |  | 2010-09-01 |  | Tunista Arctic Rim/TBI Const | PE-01 | 10501 | INSTALL UTILITIESTO FTW336A AIRCRAFT STORAGE | WWC 361 2 | 74651.2
|  |  |  | PO-104026 | Paragon General Construction | 336A AIRCRAFT 083110 | 10501 | Quality Assurance for 336A Aircraft Storage | WWC 361 2 | 80.77
|  |  | 2010-09-04 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 082810 | 10501 | Quality Assurance for 336A Aircraft Storage | WWC 361 2 | 566.28
[6 empty] | 336A AIRCRAFT 090410 | 10501 | Quality Assurance for 336A Aircraft Storage | WWC 361 2 | 143.97
|  |  | 2010-09-11 | PO-104026 | Paragon General Construction | 336A AIRCRAFT 091110 | 10501 | Quality Assurance for 336A Aircraft Storage | WWC 361 2 | 98.51
|  |  | 2010-09-21 | PO-104343 | Fosdick & Hilmer | 11932 | 10501 | Construction Consulting for FTW 336A | WWC 361 2 | 4420
|  |  | 2010-10-01 | PO-104026 | Paragon General Construction | 011 | 10501 | Quality Assurance for 336A Aircraft Storage | WWC 361 2 | 63.27
|  |  | 2010-11-02 | PO-104343 | Fosdick & Hilmer | 12031 | 10501 | Construction Consulting for FTW 336A | WWC 361 2 | 3536
|  |  | 2010-12-01 | PO-104026 | Paragon General Construction | 09182010 | 10501 | Quality Assurance for 336A Aircraft Storage | WWC 361 2 | 166.71
|  |  | 2010-11-14 | PO-104026 | Paragon General Construction | 079 | 10501 | Quality Assurance for 336A Aircraft Storage | WWC 361 2 | 1
J101397 Total | [9 empty] | 107660.23
Grand Total | [9 empty] | 1027452.68

## JobBudgetActual
Project Manager | Job Number | RFP Job No_ | Description | Division | Utility | Status | Est. Completion Date | Budget | Total POs | Total Paid on PO | Actual Costs | Difference between Budget and Commited Costs | Difference between Actual Costs and Budget
Bill Farrell | J101394 | FWA-09-021 | New EDS Utility Service for FTW 336A Aircraft | FWA | EDS | 2 | 2010-10-01 | 145000 | 140453.83 | 134808.15 | 133230.34 | 6123.98 | 11769.66
Wily Splain | J101395 | FWA-09-021 | New HDS Utility Svc for FTW 336A Aircraft Str | FWA | DHS | 2 | 2009-10-31 | 396929.04 | 567219.02 | 375945.22 | 527754.3 | -322099.06 | -130825.26
| J101396 | FWA-09-021 | New WDS Utility Svc for FTW 336A Aircraft Str | FWA | WTD | 2 | 2009-10-31 | 399178.82 | 261729.5 | 117975.93 | 258807.81 | -3382.56 | 140371.01
| J101397 | FWA-09-021 | New WWCS Utility Svc for FTW336A Aircraft Str | FWA | WWC | 2 | 2009-10-31 | 207134.23 | 41236.38 | 30628.23 | 107660.23 | 88865.85 | 99474
Grand Total | [7 empty] | 1148242.09 | 1010638.73 | 659357.53 | 1027452.68 | -230491.79 | 120789.41

## Sheet1
Status | Document No_ | Vendor Name | Line No_ | Description | Total PO Amount | Total Paid on PO | Amount left on PO | Subtotals | Vendor
2 | PO-103052 | Fosdick & Hilmer | 10000 | Professional Consulting Services for FWA 336A | 6937.5 | 6937.5 | 0 | 0
| PO-103052 Total | Fosdick & Hilmer |  |  | 6937.5 | 6937.5 | 0 | 0
| PO-103267 | Dryden & Larue Inc | 10000 | Design & Engineering Support | 20000 | 16391.95 | 3608.05 | 3608.05 | Dryden & Larue Inc
| PO-103267 Total | Dryden & Larue Inc |  |  | 20000 | 16391.95 | 3608.05 | 0
| PO-103349 | Riddle Consulting, Inc. | 38437 | Open PO for Riddle Consulting for 2010 Year | 2049.75 | 2049.75 | 0 | 0
| PO-103349 Total | Riddle Consulting, Inc. |  |  | 2049.75 | 2049.75 | 0 | 0
| PO-103730 | Fullford Electric, Inc. | 10000 | Labor to Construct FTW336A Aircraft Parts Storage | 63490 | 63490 | 0 | 0
|  | Fullford Electric, Inc. | 20000 | CO # 1 - Material and Labor for Light Pole Bases | 6018.12 | 4748.22 | 1269.9 | 1269.9 | Fullford Electric, Inc.
| PO-103730 Total | Fullford Electric, Inc. |  |  | 69508.12 | 68238.22 | 1269.9 | 0
| PO-104016 | North Coast Electric | 10000 | Misc. Materials for 336A Aircraft Part Facility | 5000 | 4232.27 | 767.73 | 767.73 | North Coast Electric
| PO-104016 Total | North Coast Electric |  |  | 5000 | 4232.27 | 767.73 | 0
| PO-103551 | Fairbanks Precast & Rebar | 40000 | SUM 1-B for New EDS Utility Service for FTW 336A | 1095 | 1095 | 0 | 0
| PO-103551 Total | Fairbanks Precast & Rebar |  |  | 1095 | 1095 | 0 | 0
| PO-103507 | Potelcom Supply | 10000 | 300kVA 12470/480 Y: Y Padmount | 10546 | 10546 | 0 | 0
| PO-103507 Total | Potelcom Supply |  |  | 10546 | 10546 | 0 | 0
| PO-103691 | Potelcom Supply | 10000 | 1/0 CONC 15kV AL, FULL NEUTRAL, 133% INSULATION | 550 | 550 | 0 | 0
|  | Potelcom Supply | 20000 | 250kcmil XHHW, 600V | 787.5 | 787.5 | 0 | 0
|  | Potelcom Supply | 30000 | #2/0 XHHW, 600V | 2710 | 2710 | 0 | 0
|  | Potelcom Supply | 40000 | #2 SECONDARY QUADRUPLEX AL UNDERGROUND | 151.5 | 151.5 | 0 | 0
|  | Potelcom Supply | 50000 | #4 XHHW, 600V | 250 | 250 | 0 | 0
|  | Potelcom Supply | 60000 | 1PH OVERHEAD CONVENTIONAL TRANSFORMER (50 kVA) | 1849.33 | 1849.33 | 0 | 0
|  | Potelcom Supply | 70000 | GROUNDING ASSEMBLY - GROUND ROD TYPE | 54.81 | 54.81 | 0 | 0
|  | Potelcom Supply | 80000 | ELBOW CONDUIT 4" RIGID STEEL SHORT SWEEP 90° 36"R | 223.3 | 223.3 | 0 | 0
|  | Potelcom Supply | 90000 | ELBOW CONDUIT 2.5" RIGID STEEL SHORT SWEEP 90°18"R | 90 | 90 | 0 | 0
|  | Potelcom Supply | 100000 | ELBOW, CONDUIT 2" RIGID STEEL SHORT SWEEP 90°24"R | 73.1 | 73.1 | 0 | 0
|  | Potelcom Supply | 110000 | 100A 240V SITE LIGHTING LOAD CENTER | 4041.63 | 4041.63 | 0 | 0
|  | Potelcom Supply | 120000 | 400A SERVICE STD BREAKER CT-CAN METER SOCKET | 4027 | 4027 | 0 | 0
|  | Potelcom Supply | 130000 | 3PH CABLE TERM. POLE DEADEND W/CUTOUTS & ARRESTERS | 1496.97 | 1496.97 | 0 | 0
|  | Potelcom Supply | 140000 | 3PH PAD MOUNTED TRANS. LOOP FEED W/RADIAL 300 kVA | 465.63 | 465.63 | 0 | 0
|  | Potelcom Supply | 150000 | SECONDARY CABLE TERMINAL POLE | 281.45 | 281.45 | 0 | 0
|  | Potelcom Supply | 160000 | GROUND ROD ASSEMBLY | 14.69 | 14.69 | 0 | 0
|  | Potelcom Supply | 170000 | CONDUIT, 4" HDPE - SCHEDULE 40 | 165.6 | 165.6 | 0 | 0
|  | Potelcom Supply | 180000 | CONDUIT, 2" HDPE - SCHEDULE 40 | 80 | 80 | 0 | 0
|  | Potelcom Supply | 190000 | CONDUIT, 1" HDPE - SCHEDULE 40 | 212.4 | 212.4 | 0 | 0
|  | Potelcom Supply | 200000 | CONDUIT, 4" GALVANIZED RIGID STEEL | 413.1 | 413.1 | 0 | 0
|  | Potelcom Supply | 210000 | CONDUIT, 2.5" GALVANIZED RIGID STEEL | 924 | 924 | 0 | 0
|  | Potelcom Supply | 220000 | CONDUIT, 2" GALVANIZED RIGID STEEL | 159.6 | 159.6 | 0 | 0
|  | Potelcom Supply | 230000 | LOAD BREAK ELBOW (200A) | 140.85 | 140.85 | 0 | 0
|  | Potelcom Supply | 240000 | #12 CU 600V, XHHW Black | 125 | 125 | 0 | 0
|  | Potelcom Supply | 250000 | #12 CU 600V, XHHW White | 125 | 125 | 0 | 0
|  | Potelcom Supply | 260000 | #12 CU 600V, XHHW Green | 125 | 125 | 0 | 0
|  | Potelcom Supply | 270000 | 30' Steel Pole | 5780 | 5780 | 0 | 0
| PO-103691 Total | Potelcom Supply |  |  | 25317.46 | 25317.46 | 0 | 0
[5 empty] | 140453.83 | 134808.15 | 5645.68 | 0
2 | PO-103052 | Fosdick & Hilmer | 20000 | Professional Consulting Services for FWA 336A | 10020.84 | 10020.84 | 0 | 0
| PO-103052 Total | Fosdick & Hilmer |  |  | 10020.84 | 10020.84 | 0 | 0
| PO-103576 | Perma-Pipe | 15000 | Direct Bury Pipe for 336A | 20143 | 20143 | 0 | 0
|  | Perma-Pipe | 16250 | Direct Bury Pipe for 336A | -16802 | -16802 | 0 | 0
|  | Perma-Pipe | 16875 | Direct Bury Pipe for 336A | 16802 | 16802 | 0 | 0
|  | Perma-Pipe | 17500 | Expedited Shipping | 4282 | 4282 | 0 | 0
|  | Perma-Pipe | 18125 | Expedited Shipping | -4282 | -4282 | 0 | 0
|  | Perma-Pipe | 18437 | Expedited Shipping | 4282 | 4282 | 0 | 0
| PO-103576 Total | Perma-Pipe |  |  | 24425 | 24425 | 0 | 0
| PO-103639 | Maynard Reece | 10000 | Prowil 3" Steam Meter #73F80-SK4AA1NAB4AA | 4935 | 4935 | 0 | 0
|  | Maynard Reece | 20000 | Plate Conditioner 35 Hole 3" #DK7ST-80K0 | 590 | 590 | 0 | 0
| PO-103639 Total | Maynard Reece |  |  | 5525 | 5525 | 0 | 0
| PO-103653 | Badger Meter | 40000 | Model 350T Transmitter for Steam Meters, 20' Lead | 210 | 210 | 0 | 0
|  | Badger Meter | 45000 | Shipping Charges | 57.28 | 57.28 | 0 | 0
| PO-103653 Total | Badger Meter |  |  | 267.28 | 267.28 | 0 | 0
| PO-103909 | Tunista Arctic Rim/TBI Const | 10000 | Utilidors and Access Vaults | 298604.8 | 250387.25 | 48217.55 | 48217.55 | Tunista Arctic Rim/TBI Const
|  | Tunista Arctic Rim/TBI Const | [5 empty] | 0
|  | Tunista Arctic Rim/TBI Const | 20000 | Utilidor and Direct Buried HDS Mains | 186628 | 186628 | 0 | 0
| PO-103909 Total | Tunista Arctic Rim/TBI Const |  |  | 485232.8 | 303529.25 | 181703.55 | 0
| PO-104026 | Paragon General Construction | 10000 | Quality Assurance for 336A Aircraft Storage | 6666.67 | 2400.42 | 4266.25 | 4266.25 | Paragon General Construction
| PO-104026 Total | Paragon General Construction |  |  | 6666.67 | 2400.42 | 4266.25 | 0
| PO-104343 | Fosdick & Hilmer | 10000 | Construction Consulting for FTW 336A | 8840 | 3536 | 5304 | 5304 | Fosdick & Hilmer
|  | Fosdick & Hilmer | 48750 | Construction Consulting for FTW 336A | 4420 | 4420 | 0 | 0
| PO-104343 Total | Fosdick & Hilmer |  |  | 13260 | 7956 | 5304 | 0
| PO-103647 | Ferguson Enterprise Inc. | 550000 | 3 IMP BLK PE A106B 40 SMLS SRL | 1825.6 | 1825.6 | 0 | 0
|  | Ferguson Enterprise Inc. | 560000 | 2 IMP BLK PE A106B 40 SMLS SRL | 69.73 | 69.73 | 0 | 0
|  | Ferguson Enterprise Inc. | 570000 | 1-1/2 IMP BLK PE A106B 40 SMLS SRL | 61.62 | 61.62 | 0 | 0
|  | Ferguson Enterprise Inc. | 580000 | 3/4 IMP BLK PE A106B 40 SMLS SRL | 28.89 | 28.89 | 0 | 0
|  | Ferguson Enterprise Inc. | 585000 | 6 BLK PE A106B 40 SMLS SRL PIPE | 56.97 | 56.97 | 0 | 0
|  | Ferguson Enterprise Inc. | 590000 | 3 CS STD WELD LR 90 ELL | 249.36 | 249.36 | 0 | 0
|  | Ferguson Enterprise Inc. | 600000 | 2 FS 3000# SOC 90 ELL | 41.78 | 41.78 | 0 | 0
|  | Ferguson Enterprise Inc. | 610000 | 3 CS STD WELD 45 ELL | 81.09 | 81.09 | 0 | 0
|  | Ferguson Enterprise Inc. | 620000 | 3 CS STD WELD TEE | 87.5 | 87.5 | 0 | 0
|  | Ferguson Enterprise Inc. | 630000 | 2 FS 3000# SOC TEE | 28.71 | 28.71 | 0 | 0
|  | Ferguson Enterprise Inc. | 640000 | 2X2X3/4 FS 3000# SOC TEE | 56.97 | 56.97 | 0 | 0
|  | Ferguson Enterprise Inc. | 650000 | 3X2 CS STD WELD ECC RED | 20.77 | 20.77 | 0 | 0
|  | Ferguson Enterprise Inc. | 660000 | 2X3/4 FS 3000# SOC RED | 36.89 | 36.89 | 0 | 0
|  | Ferguson Enterprise Inc. | 670000 | 2 FS 3000# SOC COUP | 16.32 | 16.32 | 0 | 0
|  | Ferguson Enterprise Inc. | 680000 | 3/4 FS 3000# SOC COUP | 6.26 | 6.26 | 0 | 0
|  | Ferguson Enterprise Inc. | 690000 | 2 FS 3000# SOC STL STL UNION | 35.87 | 35.87 | 0 | 0
|  | Ferguson Enterprise Inc. | 700000 | 3/4 FS 3000# SOC STL STL UNION | 22 | 22 | 0 | 0
|  | Ferguson Enterprise Inc. | 710000 | 3 CS STD WELD CAP | 16.1 | 16.1 | 0 | 0
|  | Ferguson Enterprise Inc. | 720000 | 1-1/2 FS 3000# SOC COUP | 17.01 | 17.01 | 0 | 0
|  | Ferguson Enterprise Inc. | 730000 | 3/4 TD-52 STM TRAP | 1175.76 | 1175.76 | 0 | 0
|  | Ferguson Enterprise Inc. | 740000 | 3/4 CS 600# SW PERF Y STRN | 247.39 | 247.39 | 0 | 0
|  | Ferguson Enterprise Inc. | 750000 | 3 VELAN 150# BW CS FP GATE VLV | 1077.53 | 1077.53 | 0 | 0
|  | Ferguson Enterprise Inc. | 760000 | 2 APOLLO 600# SW FP CS BALL VLV | 998.68 | 998.68 | 0 | 0
|  | Ferguson Enterprise Inc. | 770000 | 2 VELAN 800# SW CS SWING CHK VLV | 287.89 | 287.89 | 0 | 0
|  | Ferguson Enterprise Inc. | 780000 | 1-1/2 APOLLO 600# SW FP CS BALL VLV | 2745.38 | 2745.38 | 0 | 0
|  | Ferguson Enterprise Inc. | 790000 | 3/4 APOLLO 600# SW FP CS BALL VLV | 1586.15 | 1586.15 | 0 | 0
|  | Ferguson Enterprise Inc. | 800000 | 1-1/2 SS SCH10 316L A312 WELD PIPE | 1714.32 | 1714.32 | 0 | 0
|  | Ferguson Enterprise Inc. | 810000 | 1 SS SCH10 316L A312 WELD PIPE | 498.9 | 498.9 | 0 | 0
|  | Ferguson Enterprise Inc. | 820000 | 3/4 SS SCH10 316L A312 WELD PIPE | 131.44 | 131.44 | 0 | 0
|  | Ferguson Enterprise Inc. | 830000 | 1-1/2 SS 316L 3000# SOC 90 ELL | 565.25 | 565.25 | 0 | 0
|  | Ferguson Enterprise Inc. | 840000 | 1 SS 316L 3000# SOC 90 ELL | 110.57 | 110.57 | 0 | 0
|  | Ferguson Enterprise Inc. | 850000 | 3/4 SS 316L 3000# SOC 90 ELL | 148.34 | 148.34 | 0 | 0
|  | Ferguson Enterprise Inc. | 860000 | 1-1/2 SS 316L 3000# SOC 45 ELL | 221.81 | 221.81 | 0 | 0
|  | Ferguson Enterprise Inc. | 870000 | 1 SS 316L 3000# SOC 45 ELL | 55.95 | 55.95 | 0 | 0
|  | Ferguson Enterprise Inc. | 880000 | 3/4 SS 316L 3000# SOC 45 ELL | 92.65 | 92.65 | 0 | 0
|  | Ferguson Enterprise Inc. | 890000 | 1-1/2 SS 316L 3000# SOC COUP | 146.67 | 146.67 | 0 | 0
|  | Ferguson Enterprise Inc. | 900000 | 1 SS 316L 3000# SOC COUP | 28.04 | 28.04 | 0 | 0
|  | Ferguson Enterprise Inc. | 910000 | 3/4 SS 316L 3000# SOC UNION | 63.35 | 63.35 | 0 | 0
|  | Ferguson Enterprise Inc. | 920000 | 1 SS 316L 3000# SOC UNION | 25.48 | 25.48 | 0 | 0
|  | Ferguson Enterprise Inc. | 930000 | 1-1/2 APOLLO 600# SW FP CS BALL VLV | 795.56 | 795.56 | 0 | 0
|  | Ferguson Enterprise Inc. | 940000 | 1-1/2 VELAN 800# SW SS SWING CHK VL | 1492.58 | 1492.58 | 0 | 0
|  | Ferguson Enterprise Inc. | 950000 | 3/4 VELAN 800# SW SS SWING CHK VLV | 3132.97 | 3132.97 | 0 | 0
|  | Ferguson Enterprise Inc. | 960000 | 3/4 APOLLO 600# SW FP CS BALL VLV | 906.37 | 906.37 | 0 | 0
|  | Ferguson Enterprise Inc. | 970000 | 1 APOLLO 600# SW FP CS BALL VLV | 289.34 | 289.34 | 0 | 0
|  | Ferguson Enterprise Inc. | 980000 | 3/4X12 SS FLEX W/ SS SW ENDS | 363.95 | 363.95 | 0 | 0
|  | Ferguson Enterprise Inc. | 990000 | 1X12 SS FLEX W/ SS SW ENDS | 111.92 | 111.92 | 0 | 0
|  | Ferguson Enterprise Inc. | 885000 | 3/4 SS 316L 3000# SOC TEE | 47.75 | 47.75 | 0 | 0
| PO-103647 Total | Ferguson Enterprise Inc. |  |  | 21821.43 | 21821.43 | 0 | 0
[5 empty] | 567219.02 | 375945.22 | 191273.8 | 0
2 | PO-103052 | Fosdick & Hilmer | 30000 | Professional Consulting Services for FWA 336A | 10020.83 | 10020.83 | 0 | 0
| PO-103052 Total | Fosdick & Hilmer |  |  | 10020.83 | 10020.83 | 0 | 0
| PO-103490 | Panel-Fab, Inc. | 10000 | Control Panel #CP-G693 | 3748 | 3748 | 0 | 0
|  | Panel-Fab, Inc. | 20000 | PLC & HMI Configuration and Programming provided | 4200 | 4200 | 0 | 0
|  | Panel-Fab, Inc. | 40000 | Shipping | 300 | 300 | 0 | 0
| PO-103490 Total | Panel-Fab, Inc. |  |  | 8248 | 8248 | 0 | 0
| PO-103653 | Badger Meter | 10000 | 2" Recordall M170 ELL, Bare,Low Lead Alloy Housing | 464 | 464 | 0 | 0
|  | Badger Meter | 20000 | ADE and Orion Remote Module, 5/8"-2" Badger Disc | 115 | 115 | 0 | 0
|  | Badger Meter | 47500 | Shipping Charges | 91.04 | 91.04 | 0 | 0
| PO-103653 Total | Badger Meter |  |  | 670.04 | 670.04 | 0 | 0
| PO-103690 | Panel-Fab, Inc. | 10000 | Control Panel CP336AM | 789 | 789 | 0 | 0
|  | Panel-Fab, Inc. | 20000 | Estimated Shipping | 130 | 130 | 0 | 0
| PO-103690 Total | Panel-Fab, Inc. |  |  | 919 | 919 | 0 | 0
| PO-103776 | Vertex | 10000 | 6" DIP w/3" polyurethane foam | 855.4 | 855.4 | 0 | 0
|  | Vertex | 15000 | 8" DIP w/2" polyurethane foam | 1529.45 | 1529.45 | 0 | 0
| PO-103776 Total | Vertex |  |  | 2384.85 | 2384.85 | 0 | 0
| PO-103909 | Tunista Arctic Rim/TBI Const | 30000 | Utilidor and Direct Buried WDS Mains | 186628 | 186628 | 0 | 0
| PO-103909 Total | Tunista Arctic Rim/TBI Const |  |  | 186628 | 53142 | 133486 | 0
| PO-104026 | Paragon General Construction | 20000 | Quality Assurance for 336A Aircraft Storage | 6666.67 | 1703.1 | 4963.57 | 4963.57 | Paragon General Construction
| PO-104026 Total | Paragon General Construction |  |  | 6666.67 | 1703.1 | 4963.57 | 0
| PO-104343 | Fosdick & Hilmer | 20000 | Construction Consulting for FTW 336A | 8840 | 8840 | 0 | 0
|  | Fosdick & Hilmer | 49375 | Construction Consulting for FTW 336A | 4420 | 4420 | 0 | 0
| PO-104343 Total | Fosdick & Hilmer |  |  | 13260 | 13260 | 0 | 0
| PO-103647 | Ferguson Enterprise Inc. | 20000 | 8 CL53 GRVXGRV DI PIPE | 1134.97 | 1134.97 | 0 | 0
|  | Ferguson Enterprise Inc. | 30000 | 6 CL53 GRVXGRV DI PIPE | 414.2 | 414.2 | 0 | 0
|  | Ferguson Enterprise Inc. | 40000 | 2 X 20 L HARD COP TUBE (includes groove fee) | 2703.05 | 2703.05 | 0 | 0
|  | Ferguson Enterprise Inc. | 50000 | *CVR* A 8 90 LR ELL 100-C DI C/L T3 | 896.4 | 896.4 | 0 | 0
|  | Ferguson Enterprise Inc. | 60000 | 2 COP GRV 90 ELL 610 | 371.4 | 371.4 | 0 | 0
|  | Ferguson Enterprise Inc. | 70000 | 8 45 ELL 11-C CDI CL T37-77 | 291.64 | 291.64 | 0 | 0
|  | Ferguson Enterprise Inc. | 80000 | 8 TEE 20-C CDI CL T37-77 | 198.8 | 198.8 | 0 | 0
|  | Ferguson Enterprise Inc. | 90000 | *CVR* A 8X8X4 RD TEE 25-C DI C/L T3 | 451.33 | 451.33 | 0 | 0
|  | Ferguson Enterprise Inc. | 100000 | 4 PTD TRANS COUP FS M GSKT 307 | 129.75 | 129.75 | 0 | 0
|  | Ferguson Enterprise Inc. | 110000 | 4X2 PTD GRV CONC RED 50 | 51.33 | 51.33 | 0 | 0
|  | Ferguson Enterprise Inc. | 120000 | 2X1 COP GRV X COP TEE 626 | 61.68 | 61.68 | 0 | 0
|  | Ferguson Enterprise Inc. | 130000 | 2X3/4 COP GRV X COP TEE 626 | 61.65 | 61.65 | 0 | 0
|  | Ferguson Enterprise Inc. | 140000 | *CVR* A 8X6 CONC 50-C DI C/L T3 050 | 206.34 | 206.34 | 0 | 0
|  | Ferguson Enterprise Inc. | 150000 | 8 PTD GRV COUP F/ DIP 31 | 1886.96 | 1886.96 | 0 | 0
|  | Ferguson Enterprise Inc. | 160000 | 6 PTD GRV COUP F/ DIP 31 | 232.58 | 232.58 | 0 | 0
|  | Ferguson Enterprise Inc. | 170000 | 2 RIGID COUP F/ COP TUBE 607 | 699.89 | 699.89 | 0 | 0
|  | Ferguson Enterprise Inc. | 180000 | 2 COP FLG ADPT GSKT 641 | 1283.72 | 1283.72 | 0 | 0
|  | Ferguson Enterprise Inc. | 190000 | 2 BRZ 150# THRD 20 MESH Y STRN | 83.56 | 83.56 | 0 | 0
|  | Ferguson Enterprise Inc. | 200000 | 8 FLG RW OL GATE VLV W/ H/WHL ZN | 1630.77 | 1630.77 | 0 | 0
|  | Ferguson Enterprise Inc. | 210000 | 6 FLG RW OL GATE VLV W/ H/WHL ZN | 519 | 519 | 0 | 0
|  | Ferguson Enterprise Inc. | 220000 | *CVR* 317 8 CKV 317 T37H-77 T SEAT | 1638.18 | 1638.18 | 0 | 0
|  | Ferguson Enterprise Inc. | 230000 | 2 BRS 600# WOG SWT 2PC FP BV | 366.27 | 366.27 | 0 | 0
|  | Ferguson Enterprise Inc. | 240000 | 3/4 BRS 600# WOG SWT 2PC FP BV | 10.2 | 10.2 | 0 | 0
|  | Ferguson Enterprise Inc. | 250000 | 8 DI PIPE CL50 TYTON JT | 2609.12 | 2609.12 | 0 | 0
|  | Ferguson Enterprise Inc. | 260000 | 6 DI PIPE CL50 TYTON JT | 1152.24 | 1152.24 | 0 | 0
|  | Ferguson Enterprise Inc. | 270000 | 1X100 K SOFT COP TUBE | 588.79 | 588.79 | 0 | 0
|  | Ferguson Enterprise Inc. | 280000 | 8 MJ C153 90 BEND L/A | 107.49 | 107.49 | 0 | 0
|  | Ferguson Enterprise Inc. | 290000 | 1 FLR 90 BEND | 67.14 | 67.14 | 0 | 0
|  | Ferguson Enterprise Inc. | 300000 | 8X6 MJ C153 SWVL TEE L/A | 152.9 | 152.9 | 0 | 0
|  | Ferguson Enterprise Inc. | 310000 | 8 ROMAGRIP ACCY PK F/ DI | 442.96 | 442.96 | 0 | 0
|  | Ferguson Enterprise Inc. | 320000 | 6 ROMAGRIP ACCY PK F/ DI | 573.28 | 573.28 | 0 | 0
|  | Ferguson Enterprise Inc. | 330000 | 1 FLR X MIP COUP | 42.59 | 42.59 | 0 | 0
|  | Ferguson Enterprise Inc. | 340000 | 6 MJ RW DI OL GATE VLV L/A | 496.62 | 496.62 | 0 | 0
|  | Ferguson Enterprise Inc. | 350000 | 5x5 SV SH soil pipe | 91.6 | 91.6 | 0 | 0
|  | Ferguson Enterprise Inc. | 360000 | 18 TOP SECTION F/ VB | 30.22 | 30.22 | 0 | 0
|  | Ferguson Enterprise Inc. | 370000 | 1 BOT SECT F/ VB | 33.9 | 33.9 | 0 | 0
|  | Ferguson Enterprise Inc. | 380000 | PAVING SLV LID ONLY - WTR | 10.48 | 10.48 | 0 | 0
|  | Ferguson Enterprise Inc. | 390000 | VLV BX DUST CUP | 9.66 | 9.66 | 0 | 0
|  | Ferguson Enterprise Inc. | 400000 | 5-1/4 BURY HYD 5'0 16 TRAFFIC 6 FLG | 1922.18 | 1922.18 | 0 | 0
|  | Ferguson Enterprise Inc. | 410000 | 4X5X53 STL HYD MRKR W/ POLY FLAG | 32.42 | 32.42 | 0 | 0
|  | Ferguson Enterprise Inc. | 420000 | 6 FLG TYTE GSKT | 11.43 | 11.43 | 0 | 0
|  | Ferguson Enterprise Inc. | 430000 | 6 150# BOLT KIT 8 3/4X3-1/4 IMP | 9.01 | 9.01 | 0 | 0
|  | Ferguson Enterprise Inc. | 440000 | 6 MJ C153 ACC PK | 15.17 | 15.17 | 0 | 0
| PO-103647 Total | Ferguson Enterprise Inc. |  |  | 23722.87 | 23722.87 | 0 | 0
| PO-103701 | CB Engineering Pacific Inc. | 10000 | Greystone Ambient air Temp. Trans.#TE500AS12GS003 | 136.74 | 136.74 | 0 | 0
|  | CB Engineering Pacific Inc. | 20000 | Greystone Temp/Humd Trans. #RH310A03C1A6 | 253.07 | 253.07 | 0 | 0
|  | CB Engineering Pacific Inc. | 30000 | Direct Mount Gauge Pressure Transmitter | 642.81 | 642.81 | 0 | 0
|  | CB Engineering Pacific Inc. | 50000 | Two Valve Manifold #PV-614SCG | 237.92 | 237.92 | 0 | 0
|  | CB Engineering Pacific Inc. | 60000 | Differential Pressure Transmitter | 989.45 | 989.45 | 0 | 0
|  | CB Engineering Pacific Inc. | 80000 | 12" Verabar Primary Flow Element | 2012.9 | 2012.9 | 0 | 0
|  | CB Engineering Pacific Inc. | 100000 | Honeywell Limit Switch #BZE6-2RN2 | 147.34 | 147.34 | 0 | 0
|  | CB Engineering Pacific Inc. | 110000 | Greystone Outside Ambient Air Temp. Trans. | 237.65 | 237.65 | 0 | 0
|  | CB Engineering Pacific Inc. | 130000 | Temp. Transmitter #YTA110-EA2DN/FU1/D2 | 681.03 | 681.03 | 0 | 0
|  | CB Engineering Pacific Inc. | 140000 | Temperature Sensor with Thermowell | 280.18 | 280.18 | 0 | 0
|  | CB Engineering Pacific Inc. | 160000 | Estimated Shipping | 358.4 | 358.4 | 0 | 0
| PO-103701 Total | CB Engineering Pacific Inc. |  |  | 5977.49 | 5977.49 | 0 | 0
| PO-103511 | GE Intelligent Platforms | 10000 | I/O Filler Module #IC200ACC301 | 23.4 | 23.4 | 0 | 0
|  | GE Intelligent Platforms | 20000 | I/O Shorting Bar QTY2 #IC200ACC303 | 33.6 | 33.6 | 0 | 0
|  | GE Intelligent Platforms | 30000 | Analog input 16 bit voltage/current 8 isolated ch. | 2155.2 | 2155.2 | 0 | 0
|  | GE Intelligent Platforms | 50000 | Compact I/O carrier box style#IC200CHS022 | 456 | 456 | 0 | 0
|  | GE Intelligent Platforms | 60000 | CPU 128K User Config. User Memory #IC200CPUE05 | 783.6 | 783.6 | 0 | 0
|  | GE Intelligent Platforms | 70000 | Input 24VDC POS/NEG Logic 16 Points#IC200MDL640 | 87 | 87 | 0 | 0
|  | GE Intelligent Platforms | 80000 | Output 12/24VDC POS Logic 16 Point#IC200MDL740 | 176.4 | 176.4 | 0 | 0
|  | GE Intelligent Platforms | 90000 | Power Supply w/ Expanded 3.3VDC 24 VDC Input | 39 | 39 | 0 | 0
|  | GE Intelligent Platforms | 110000 | View Intermediate 6" STN Touch DC #IC754VSI06STD | 1576.5 | 1576.5 | 0 | 0
|  | GE Intelligent Platforms | 120000 | Shipping Estimated | 306.89 | 306.89 | 0 | 0
|  | GE Intelligent Platforms | 138750 | Analog input 16 bit voltage/current 8 isolated ch. | -1077.6 | -1077.6 | 0 | 0
|  | GE Intelligent Platforms | 139687 | Compact I/O carrier box style#IC200CHS022 | -228 | -228 | 0 | 0
|  | GE Intelligent Platforms | 139843 | CPU 128K User Config. User Memory #IC200CPUE05 | -783.6 | -783.6 | 0 | 0
|  | GE Intelligent Platforms | 139896 | CPU 128K User Config. User Memory #IC200CPUE05 | 783.6 | 783.6 | 0 | 0
|  | GE Intelligent Platforms | 139950 | Output 12/24VDC POS Logic 16 Point#IC200MDL740 | -88.2 | -88.2 | 0 | 0
|  | GE Intelligent Platforms | 139995 | View Intermediate 6" STN Touch DC #IC754VSI06STD | -788.25 | -788.25 | 0 | 0
|  | GE Intelligent Platforms | 139997 | Shipping Estimated | -223.79 | -223.79 | 0 | 0
| PO-103511 Total | GE Intelligent Platforms |  |  | 3231.75 | 3231.75 | 0 | 0
[5 empty] | 261729.5 | 117975.93 | 143753.57 | 0
2 | PO-103052 | Fosdick & Hilmer | 40000 | Professional Consulting Services for FWA 336A | 10020.83 | 10020.83 | 0 | 0
| PO-103052 Total | Fosdick & Hilmer |  |  | 10020.83 | 10020.83 | 0 | 0
| PO-103776 | Vertex | 20000 | 6" DIP w/3" polyurethane foam | 3581.4 | 3581.4 | 0 | 0
| PO-103776 Total | Vertex |  |  | 3581.4 | 3581.4 | 0 | 0
| PO-104026 | Paragon General Construction | 30000 | Quality Assurance for 336A Aircraft Storage | 6666.66 | 1362.51 | 5304.15 | 5304.15 | Paragon General Construction
| PO-104026 Total | Paragon General Construction |  |  | 6666.66 | 1362.51 | 5304.15 | 0
| PO-104343 | Fosdick & Hilmer | 30000 | Construction Consulting for FTW 336A | 8840 | 8840 | 0 | 0
|  | Fosdick & Hilmer | 49687 | Construction Consulting for FTW 336A | 4420 | 4420 | 0 | 0
| PO-104343 Total | Fosdick & Hilmer |  |  | 13260 | 7956 | 5304 | 0
| PO-103647 | Ferguson Enterprise Inc. | 450000 | 6 DI PIPE CL50 TYTON JT | 4824.22 | 4824.22 | 0 | 0
|  | Ferguson Enterprise Inc. | 460000 | 6 MJ C153 90 Bend L/A | 241.42 | 241.42 | 0 | 0
|  | Ferguson Enterprise Inc. | 470000 | 6 MJ C153 45 Bend L/A | 419.8 | 419.8 | 0 | 0
|  | Ferguson Enterprise Inc. | 480000 | 8X5 DI TRANS COUP 9.06-9.06 | 324.2 | 324.2 | 0 | 0
|  | Ferguson Enterprise Inc. | 490000 | 6 MJ C153 ACC PK | 716.69 | 716.69 | 0 | 0
|  | Ferguson Enterprise Inc. | 500000 | 8 MJ C153 ACC PK | 38.84 | 38.84 | 0 | 0
|  | Ferguson Enterprise Inc. | 510000 | 6 MJ C153 SLD CAP L/A | 116.49 | 116.49 | 0 | 0
|  | Ferguson Enterprise Inc. | 520000 | 6 MJ C153 WYE L/A | 840.36 | 840.36 | 0 | 0
|  | Ferguson Enterprise Inc. | 530000 | 8X6 MJ C153 WYE L/A | 185.47 | 185.47 | 0 | 0
| PO-103647 Total | Ferguson Enterprise Inc. |  |  | 7707.49 | 7707.49 | 0 | 0
[5 empty] | 41236.38 | 30628.23 | 10608.15
[5 empty] | 1010638.73 | 659357.53 | 351281.2
73701.2
[9 empty] | Dryden & Larue Inc | 3608.05
[9 empty] | Fullford Electric, Inc. | 1269.9
[9 empty] | North Coast Electric | 767.73
[9 empty] | Tunista Arctic Rim/TBI Const | 48217.55
[9 empty] | Fosdick & Hilmer | 5304
[9 empty] | Paragon General Construction | 14533.97
73701.2