| To: | Syd |
| --- | --- |
| From: | Norman |
| Date: | 4/4/2014 |
| Subject: | CLIN 0084 |
| Project: | FTW 336A Aircraft Parts Storage |
| Project #: | FWA-09-021 |

Overview

On September 16, 2009, DU received a Notice to Proceed (NTP) on the design and engineering of the FWA-09-021 project with a budget of $1,170,387.00.  This project, to install new water, wastewater, & heat distribution systems to the FTW-336A Aircraft Storage Facility, closed Dec. 2010, was completed with a budget of at most $1,210,875.00 surpassing expected budget by approximately $40,000 or about 3%.

Chronology of Events

8/11/09 – 	DU receives RFP

9/03/09 – 	DU submits RFP response (design and engineering)

9/16/09 – 	NTP for design and engineering received (based on 9/3/09 proposal)

11/2/09 – 	DU submits RFP response for construction portion of project

2/24/10 – 	NTP for construction received (based on 11/2/09 proposal)

7/02/10-	Contract signed with TAR/TBI Construction LLC for project construction

8/08/10-	Tunista submits DCVR #7 proposing enlarging the manhole to accommodate the piping configurations and the construction joints.

9/11/10	Tunista notifies DU they have encountered contaminated soil, have stopped work, and awaiting direction

9/13/10	DU (Wily) notifies DPW of contaminated soil conditions.

1/13/10	Tunista submits change order #1 with all costs associated with construction joint, contaminated soil removal, DCVR’s, and change proposals.

1/19/11 – 	DU submits letter to DLA with brief explanation of overruns

1/19/11 – 	Jim Slicker e-mails DU indicating that 1/19/11 letter insufficient

Narrative of Events

DU received RFP FWA-09-21 on August 11, 2009. The RFP was for design effort only and required a cost estimate. The proposal due date was August 26, 2009.  DU responded to the RFP on 9/03/09 with a cost estimate of $60,000 for design services.  DU receives NTP for design services on September 16, 2009 with a requested proposal due date of October 30, 2009.

On November 2, 2009 DU submits the response to the RFP with a cost estimate ($1,110,387) for the construction of the project and an expected construction completion date of August 31, 2010 assuming DU receives a timely NTP (February 15, 2010).

On February 24, 2010 DLA issues the NTP for DU to proceed with construction of the project.

On 7/02/2010  Tunista Arctic Rim/TBI Construction LLC signs the contract for construction of the project.

On 8/08/2010  Kris Manke of TAR/TBI submits DCVR #7 stating that due to the new manhole location, the manhole size and the piping configuration that they are having a difficult time making the plans work. They suggest enlarging the manhole to accommodate the ladder placement and piping. Trying to tie into the utilidor at any other point would be dangerous due to the placement of the construction joints. Design Engineer F&H recommends submitting a change order proposal for the work. In addition, the proposal should incorporate a 12” increase in depth.

On 9/11/2010 (Saturday)  Scott Winner of  TAR/TBI notifies Wily they have hit contaminated soil during excavation for the direct bury piping between aircraft storage and building 2077. Work has stopped and excavation cannot be completed. Awaiting advise from DU for corrective action.

On 9/13/2010 (Monday) DU (Wily) notifies DPW of the contaminated soil conditions. He also states that TAR/TBI does not have enough room onsite to segregate the contaminated soil but they have created a cell for contaminated soil at a separate project. They have requested permission to use the same area for the FTW 336A contaminated soil and are ready to discuss costs. DU (Wily) requests discussion at DPW’s earliest convenience and states he will call ASAP.

On 9/16/2010 at DPW meeting Wily notes again of the contaminated soil conditions and gives an update of the sampling and analysis plan to ADEC and DPW.

On 1/13/2010 TAR/TBI submits change order #1 for $95,026 including all the accrued additional project construction costs for DCVR’s, and CP’s. The costs include larger manhole construction, contaminated soil removal, design changes, missing materials (perma-pipe), moving poles, heat trace, and installation of additional instrumentation (design addendum).

On 1/19/2011 DU submits a letter to DLA stating the project costs will overrun the budget by approximately $40K due to change orders due to two unanticipated conditions including excavation into unknown contaminated soil and discovery of unsafe utilidor joint.

On 1/19/2011 Jim Slicker e-mails that the DU letter is not sufficient to verify the request for an additional $40K and that we did not notify them in writing (or an e-mail) of the changing site conditions. They state this additional funding request will sit until the backup package (justification narrative and clear cost backup) comes in for their evaluation.

Costs

Cost Estimate (F&H)	$1,110,387

Project Budget		$1,170,387

TAR/TBI Contract	$746,512

Final Costs		$1,210,999

Cost Overrun		$1,210,999 - $1,170,387 = $40,612

Summary

TAR/TBI Construction signed the contract for construction of FTW 336A on 7/02/2010. A series of events and design issues through the project life pushed the project costs over the budget amount. These included building an enlarged manhole to meet construction joints, contaminated soil removal, design changes, missing materials, removal and relocation of a power pole, installation of additional heat trace, and installation of additional instrumentation (design addendums). The DCVR and CP project costs were not accounted for until a change order #1 was submitted at the end of the project for $95,026. These additional costs contributed the total project costs to exceed the budget by $40,612.